## APP-NAPSA CONS GUIDES-2018 (hidden)
NATIONAL PENSION SCHEME AUTHORITY
Guidelines on the Conslidated 2019 Annaul Procurement Plan for Consultancy Services
1. | An Annual Procurement Plan (APP) is a mandatory feature of the procurement policy framework as articulated in Public Procurement Act No. 12 of 2008. The approval of APP by the Executive Management Committee and Management Procurement Committee of NAPSA is used to achieve the requirement that all procurement must have the approval of the Budget Approving Authority. It is further used as a monitoring tool to ensure that all planned procurement follow the procedures and target dates.
2. | The consolidated Annual Procurement Plan for Consultancy Services has been prepared to fulfill the requirements of Public Procurement Act No. 12 of 2008 and Public Procurement Regulation in accordance with NAPSA Procurement Policy Manual.
3. | Three kinds of APP formats are introduced in this Guideline as shown below. A Soft Copy of the Guideline is contained in a Worksheet designated as APP-NAPSA CONS 2019.
| 3.1 | APP for Internal Use: This format is contained in a Worksheet designated as APP-CONS-NAPSA 2019. It gives detailed information about each procurement to be carried out by a NAPSA including key dates for which certain actions must be completed by its staff to ensure that there is no delay in the procurement process. For each tender, two rows are provided: one for recording the planned dates for various actions and one for filling in actual dates when the actions were implemented.
| 3.2 | APP for External Use: This format is contained in a Worksheet designated as APP-CONS-NAPSA 2019 EU. It gives detailed information about each procurement to be carried out by NAPSA through open competition and it forms part of the Natiional Competitive Method to be made available to potential consultants. It aims at notifying potential consultants of procurement opportunities available in the Authority. In this format information regarding particulars of the assignments, dates for advertisement, dates for invitation to submit proposals and notification of consultants are given.
| 3.3 | APP for Submission to ZPPA: This format is contained in a Worksheet designated as APP-CONS-NAPSA ZPPA-19. It gives detailed information about each procurement to be carried out by a NAPSA including key dates for notifying potential consultants of the tender proceedings and results of the tender process. This is required to be submitted to ZPPA at the start of the financial year to enable ZPPA be aware of the procurement volume for that particular year and enable it plan its monitoring activities accordingly.
4. | Abbreviations used in this Guideline
| APP | Annual Procurement Plan
| PPR | The Public Procurement Regulations, No, 63 of 2011
| NAPSA | National Pension Scheme Authority (NAPSA)- Procuring Entity
| PSU | Procurement and Stores Department
| PPA 2008 | Public Procurement Act No. 12 of 2008
| ZPPA | Zambia Public Procurement Authority
| RFP | Request for Proposal
| FP | Financial Proposal
| TP | Technical Proposal
Column No. | Guidance on the Information to be filled in the respective column of the Format |  | Corresponding Column in the APP format for External Use | Corresponding Column in the APP format for Submission to ZPPA
01-06 | These columns gives details of various tenders to be floated by the NAPSA, their estimated values and selected procurement methods |  | 01-06 | 01-04
01. | This column include a brief description of the Consultancy Assignment e.g. Consultancy Services for external Audit for NAPSA |  | 01 | 01
02. | This column include the designated tender number. For easy identification of the NAPSA (where applicable) the tender number shall be preceded by the code number of the NAPSA and the respective financial year. For example, if the code number of the NAPSA is P01 and the financial year is 2019 the tender numbers shall be preceded by P01-2019 to assist with allocation of tender numbers to each tender. |  | 02 | 02
03. | This column indicate lot numbers in case of a tender divided into lots. When there is only one lot, this shall be shown in this column as a single lot. |  | 03 | 03
04. | This column indicate the estimated value of the procurement for each lot. The estimated value shall to a large extent reflect the budgeted amount for that procurement. To assist NAPSA to prepare correct estimates, the NAPSA market research shall prepare price indices for various items based on consultancy assignments carried out in the previous years and market trends. |  | This information is not required for disclosure to the potential tenderers as it will tend to influence prices | 04
05 | In this column the method of selection adopted is given. Determination of the appropriate selection method shall be done in accordance with Public Procurement Act and NAPSA Procurement Policy Manual. |  | 05 | 06
06 | Indicate the selected type of contract. |  | 06 | 07
o7 | In this column, User department are mandated with responsibility to provide TORs or functional specifications for software before any procurement process begins. Any delay here is negatively likely the entire process. User departments should pay attention to this date. Procurement may begin earlier or later provided implementation is affected by cashflow.
08 | For tenders where open competitive methods have been found to be appropriate, they shall be advertised in the media. The date earmarked for the Advert is shown in this column. To cut down on the costs of advertising, NAPSA should consider using a minimum number of Advert consisting of several tenders. |  | This is required to ensure consolidation of tenders | 08
09-12 | These columns apply for Tenders where Invitation of Expression of Interest need to be carried out prior to inviting tenders. |  | 07-09 | 09-11
09. | This column indicate the date when NAPSA expects to advertise for the Invitation for Expression of Interest |  | 07 | 09
10. | This column indicate the expected deadline for the submission and opening of the Expression of Interest entries. Statutory periods from the date of advertising to the submission of the applications are given. They are 30 days and 14 days for the international and national competitive selection respectively. |  | 08 | 10
11. | In this column, the NAPSA indicate the deadline by which the evaluation of Expression of Interest entries must be completed to ensure that subsequent stages of the procurement are not affected.. |  | This information is for internal use to the NAPSA
12. | This column indicates the deadline by which the Expression of Interest evaluation report must be approved by the MPC in order to ensure that subsequent stages of the procurement are not affected. |  | The successful applicants must be immediately be informed after the approval of shortlist is done by the MPC | 11
13-24 | These columns gives the details of the actual tender process starting from the preparation of tendering documents to the approval of award of contract. |  | 10-12 | 12-15
13 | In this column, User department are mandated with responsibility to provide TORs or functional specifications for software before any procurement process begins when the process begins with RFP. Any delay here is negatively likely the entire process. User departments should pay attention to this date. Procurement may begin earlier or later provided implementation is affected by cashflow.
14 & 15 | In this column, the NAPSA indicate the deadline by which the RFP Document must be ready by PSU and submitted for approval by the Procurement/Contract Review Committee in order to ensure that subsequent stages of the procurement are not affected.This deadline may be in parallel with deadlines for actions under those columns 09 to 12. User department strictly urged to prepare TORs in advance to avoid delaying the procurement process. |  | This information is for internal use to the NAPSA
16 | In this column, NAPSA obtains clearance of Direct Bidding to get "No Objection" from ZPPA for financial thresholds above fifty Thousand Kwacha and to deviate from Open Selection to use Limited selection.
17. | This column indicates the deadline by which the RFP Document must be approved by the Procurement/Contract Review Committee in order to ensure that subsequent stages of the procurement are not affected. The approval of bidding can be delegatede to PSU. In cases of tenders with Invitation for Expression of Interest, in order to avoid delays, this date could be the same as that appearing in column 12
18. | This column shall indicate the date when the NAPSA expects to issue of RFP documents to the shortlisted consultants. |  | 10 | 12
19. | This column indicate the expected deadline for the submission and opening of the RFP. Statutory periods from the date of invitation to the submission of the proposals are given in the NAPSA Procurement policy manual. They are 45 days and 30 days for the international and national competitive selection respectively. |  | 11 | 13
20. | In this column, NAPSA indicate the deadline by which the evaluation of TP must be completed to ensure that subsequent stages of the procurement are not affected.. |  | This information is for internal use to the NAPSA
21. | This column indicates the deadline by which the TP evaluation report must be approved by the MPC.
22. | This column indicates the set date for opening of FP. Normally it is two weeks from the date specified in Column 18. A shorter period may be fixed if all Consultants have qualified to have their FP opened and have confirmed to attend the opening meeting
23. | This column indicates the deadline by which the Combined evaluation report must be completed. |  | This information is for internal use to the NAPSA
24. | This column indicates the deadline by which the combined evaluation report must be approved by MPC |  | All bidders must immediately be informed after the decision of contract award is done by the MPC to commence the 10 day window for compalnts | 14/15
25-27 | These columns gives the details of the final actions towards formalization of the contract.
27 | In this column the amount of the contract award is inserted. In the planned row it is expected to insert the estimated (budgeted amount) of the particular tender. In the actual row NAPSA shall insert the amount of the contract award approved by the MPC |  | This information is for internal use to the Authority. However ZPPA shall obtain the award information on the Reports to be submitted on the implementation of each procurement
28 | In this column NAPSA shall fill in the expected date for contract for contract award. For planning purposes this date shall be the determinant of the dates by which the preceding actions must be completed so that the award of the contract is made by this date
29 | In this column the NAPSA indicate the expected date for signing of the contract.
This plan will be updated quarterly as and when quarterly reports will be submitted to ZPPA
For More Information and Guidance, Contact
Head Procurement & Stores
National Pension Scheme Authority
NAPSA Head Office
P.O. Box 51275, Lusaka
Tel. No. +260 211 228046/8
Fax. No. +255 22 2121238
E-mail: MwiingaJ@napsa.co.zm
Website: www.napsa.co.zm

## APP-NAPSA Guides GWNCS 2019 (hidden)
NATIONAL PENSION SCHEME AUTHORITY
Guidelines on the preparation of the NAPSA 2019 consolidated Procurement Plan for Goods, Works and Non-Consultancy Services
1. | An Annual Procurement Plan (APP) is a mandatory feature of the procurement policy framework as articulated in PPA Act no.12 of 2008. The approval of APP by the Executive Management Committee of the Authority is used to achieve the requirement that all procurement must have the approval of the Management Procurement Committee . It is further used as a monitoring tool to ensure that all planned procurement follow set procedures and target dates.
2. | The Procurement Plan for Goods, Works and Non-Consultancy Services has been prepared to fulfill the requirements of Public Procurement Act no. 12 of 2008 and the Public Procurement Regulations no. 63 of 2011.
3. | Three kinds of APP are introduced in this Guideline as shown below. A Soft Copy of the Guideline is contained in a Worksheet designated as Consolidated NAPSA Annual Procurement Plan 2019.
| 3.1 | APP for Internal Use: It gives detailed information about each procurement to be carried out by NAPSA including key dates for which certain actions must be completed by its staff to ensure that there is no delay in the procurement process. For each tender, two rows are provided: one for recording the planned dates for various actions and one for filling in actual dates when the actions were implemented as a guide.
| 3.2 | APP for External Use: It gives detailed information about each procurement to be carried out by NAPSA through open competition and it forms part of the ZPPA website advert to be made available to potential bidders. It aims at notifying potential bidders of procurement opportunities available in NAPSA. In this extract format a mirror of the detailed consolidated APP information regarding particulars of tender, dates for advertisement and notification of bidders are given.
| 3.3 | APP for Submission to ZPPA: . It gives detailed information about each procurement to be carried out by NAPSA including key dates for notifying potential bidders of the tender proceedings and results of the tender process. This is required to be submitted to ZPPA at the start of the financial year in compliance with the Public Procurement Act No12 of 2008 and regulations to enable ZPPA be aware of the procurement volume for that particular year and enable to plan its monitoring activities accordingly.
4. | Key Abbreviations used in this Guideline
| APP | Annual Procurement Plan
| PPR | The Public Procurement Regulations, No.63 of 2011
| NAPSA | National Pension Scheme Authority (NAPSA)- Procuring Entity
| PSU | Procurement and Stores Department
| PPA | Public Procurement Act No 12 of 2008
| ZPPA | Zambia Public Procurement Authority
Column No. | Guidance on the Information to be filled in the respective column of the APP |  | Corresponding Column in the APP format for External Use | Corresponding Column in the APP format for Submission to ZPPA
01-06 | These columns gives details of various tenders to be floated by the NAPSA, their estimated values and selected procurement methods |  | 01-04 | 01-04
01. | This column include a brief description of the Tender e.g. Tender for the Supply of Office Stationery |  | 01 | 01
02. | This column include the designated tender number (where applicable). For easy identification of the Authority. NAPSA shall issue Code Numbers (where necessary). The tender number shall be preceded by the code number of the Authority and the respective financial year. For example, if the code number of the Department is P01 and the financial year is 2019, the tender numbers shall be preceded by P01-2019 and will guide Procurement to issue tender numbers during implementation of the APP. |  | 02 | 02
03. | This column indicate lot numbers in case of a tender divided into lots. When there is only one lot, this shall be shown in this column as a single lot. |  | 03 | 03
04. | This column indicate the estimated value of the procurement for each lot. The estimated value shall to a large extent reflect the budgeted amount for that procurement in line with 2019 NAPSA Budget. To assist NAPSA Directorates/ departments to prepare correct estimates, the Departments use estimates as per approved budgets to prepare price indices for various items based on tenders carried out in the previous years and market trends. Where the columns are shaded blue it indicates that the Authority shall consolidate like items as one procurement to avoid split buying. The principle of consolidation likey to apply where ever applicable. |  | This information is not required for disclosure in the final APP given to users and ZPPA to the potential bidders as it will tend to influence prices | 04
05. | Procurement method to be adopted is shown in this column. Determination of the appropriate method is guided by the NAPSA Procurement Policy Procedure manual for Procurement of Goods Works and Non-Consultant Services and the Public Procurement Act no.12 of 2008. |  | 04 | 05
06. | For tenders where open tendering methods have been found to be appropriate, they shall be advertised in the Press (media). The date earmarked for the advert shall be shown in this column. To cut down on the costs of advertising, the Authority should consider using a minimum number of adverts consisting of several tenders. |  | This is not required since the whole of this document consist advert | 06
07-13 | These columns apply for Tenders where pre-qualification of bidders need to be carried out prior to inviting tenders. |  | 05-07 | 07-09
o7 | In this column, User department are mandated with responsibility to provide Specifications, BOQs or TORs before any procurement process begins. Any delay here is negatively likely the entire process. User departments should pay attention to this date. Procurement may begin earlier or later provided implementation is affected by cashflow.
08. | In this column, the Authority indicate the deadline by which pre-qualification documents must be ready for approval in order to ensure that subsequent stages of the procurement are not affected.. |  | This information is for internal use to the Authority
09. | This column indicates the deadline by which pre-qualification documents must be approved by the PCRC in order to ensure that subsequent stages of the procurement are not affected. The approval of the documents can be delegated to the PSU.
10. | This column indicate the date when the Authority expects to advertise for the pre-qualification process. |  | 05 | 07
11. | This column indicate the expected deadline for the submission and opening of the pre-qualification entries. Statutory periods from the date of advertising to the submission of the applications are 30 days and 21 days for the international and national competitive bidding respectively. |  | 06 | 08
12. | In this column, the Authority indicate the deadline by which the evaluation of pre-qualification entries must be completed to ensure that subsequent stages of the procurement are not affected.. |  | This information is for internal use to the Authority
13. | This column indicates the deadline by which the pre-qualification evaluation report must be approved by the Management Procurement Committee in order to ensure that subsequent stages of the procurement are not affected. This shall also be the date for notifications of the outcome of the pre-qualification process. |  | 07- The successful applicants must be immediately be informed after the approval of shortlist is done by the MPC | 09
14-24 | These columns gives the details of the actual tender process starting from the preparation of bidding documents to the approval of award of contract. |  | 08-10 | 10-13
14 | In this column, User Directorates/department are mandated with responsibility to provide Specifications, BOQs or TORs before any procurement process begins when you use RFP/SD from start. Any delay here is negatively likely to affect the entire process. User departments should pay attention to this date. Procurement may begin earlier or later provided implementation is not affected by cashflow.
15. | In this column, the Authority indicate the deadline by which the Solicitation Document must be ready for approval in order to ensure that subsequent stages of the procurement are not affected.This deadline may be in parallel with deadlines for actions under columns 07 to 12. |  | This information is for internal use to the Authority
16 | In this column, NAPSA is required to get "No Objection" from ZPPA for thresholds above ten Thousand Kwacha when using Direct Bidding, serve for items covered by ZPPA circular no. 3 of 2017..
17 | In this Column, NAPSA is expected to seek MPC authority to use limited bidding/selection when there is deviation from National Competitive Bidding as required by the Authority or user.
18 | This column indicates the deadline by which the Tender Document/SD must be approved by the Procurement and Contract Review Committee in order to ensure that subsequent stages of the procurement are not affected. The approval of the document can be delegated to the PSU. In cases of tenders with pre-qualification, in order to avoid delays, this date could be the same as that appearing in column 11
19 | This column indicate the date when the Authority expects to advertise for the tender or to start to issue solicitation documents to the shortlisted bidders in the case of a tender with pre-qualification. In all cases the user department must trigger the procurement process by providing the Specifications, BOQs or TORs. Without this information the tender process may delay or fail to achieve value for money |  | 08 | 10
20 | This column indicate the expected deadline for the submission and opening of the tenders. Statutory periods from the date of advertising to the submission of tenders are 45 days and 30 days for the international and national competitive bidding respectively. Where large works are involved this could take longer. |  | 09 | 12
21 | In this column, the Authority shall indicate the deadline by which the evaluation of tenders must be completed to ensure that subsequent stages of the procurement are not affected. Evaluation should be completed between 1 to 3 weeks depending on the procurement method used and complexity and nature of procurement. Agreed SLA duration is 2 weeks. |  | This information is for internal use to the Authority
22 | This column indicates the deadline by which the tender evaluation report must be approved by the MPC. This shall also be the date for notifying the winner or all bidders for National Competitive bidding. |  | 12 | 13
23 | In this column the MPC through the PSU indicate the expected date of Notice of intention to award. All bidders must immediately be informed after the decision of contract award is done by the MPC to commence the 10 day window for complaints for National and international bidding process. |  | 10 | 13
24 | In this column the Authority Contract Officer is expected to indicate date of submission of a draft contract for Vetting by the Attorney General or date of submission of a draft contract for Ratification by Legal Counsel of NAPSA. The Legal Counsel in liaison with Contract Officer and Legal Contract, Manager shall, within three working days after being notified by the MPC of its award decision for award acceptance whose value is five Hundred Thousand kwacha or more, submit to the Attorney General the draft contract for vetting and review within twenty one working days upon receiving it. For contracts between one hundred Thousand kwacha and Five Hundred Thousand kwacha depending on nature and urgency may be issued with local purchase order unless nature of purcahse is compelling to have a formal contract drawn. Acceptance of tender whose value is below one hundred Thousand kwacha shall be through local purchase orders within seven working days upon receiving approved requisition. |  | 11 | 14
25-27 | These columns gives the details of the final actions towards formalization of the contract.
25 | In this column the amount of the contract award shall be inserted. In the planned row it is expected to insert the estimated (budgeted amount) of the particular tender. In the actual row the Authority insert the amount of the contract award approved by the MPC or Director General depending on the procurement thresholds. |  | This information is for internal use to the Authority. However ZPPA shall obtain the award information on the Reports to be submitted on the implementation of each procurement as required under the Public Procurement Act No 12 of 2008.
26 | In this column the Authority indicate the expected date for contract award. For planning purposes this date shall be the determinant of the dates by which the preceding actions must be completed so that the award of contract is made by this date.
27 | In this column the Authority shall fill in the expected date for signing of the contract.
28 | This plan will be updated quarterly alongside with submission of quarterly reports to ZPPA
For More Information and Guidance, Contact
Head Procurement & Stores
National Pension Scheme Authority
NAPSA Head Office
P.O. Box 51275, Lusaka
Tel. No. +260 211 228046/8
Fax. No. +255 22 2121238
E-mail: MwiingaJ@napsa.co.zm
Website: www.napsa.co.zm

## APP-GWNCS-NAPSA 2020
PROCUREMENT PLAN FOR GOODS, WORKS AND NON-CONSULTANCY SERVICES - INTERNAL USE
Name of Procuring Entity:
FINANCIAL YEAR |  | 2018
Description | User | QTY | Lot Number |  |  |  | PRE-QUALIFICATION |  |  |  | PRE-QUALIFICATION |  | TENDERING DOCUMENTS |  |  |  |  | Invitation for Tenders and Evaluation | [5 empty] | Contract Finalization |  |  |  | Plan vs. Actual | Comment
[7 empty] | DOCUMENT |  | INVITATION |  | EVALUATION | [6 empty] | Invitation for Tendering |  | Tender Evaluation and approval of award
|  |  |  | Estimated amount ZMW | Procurement Method | Submission of Specs, TORs or BOQS by User | Preparation by PSU | Approval by MPC/ PPP | Invitation Date | Closing-Opening Date | Submission Eval Rpt | Approval by MPC/PPP | Submission of Specs, TORs or BOQS by User | Prep & Submission by PSU | Clearance By ZPPA for Direct Bidding | Approval By MPC to use Limited/Direct Bidding | Clearance of Solicitation Document by MPC/ End User | Tender Invitation Date/ RFQ | Tender Closing-Opening | Submission Tender Eval Rpt/ Tender Analysis | Approval by MPC (DG) | Notice of intention to award Date | Vetting/ Approval of contract by AG | Contract Amount in ZMK. 000 | Date Contract Award | Date Contract/LPO Signature | Estimated Contract Completion Date
1 | 2 | 3 | 4 |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
(Normal Duration of Procurement Steps) | [6 empty] | 1 - 1.5 wks | 0.5 wk | 1 wk | 4 wks | 1-3 wks | 1 wk | 2 Wks | 1 wk | 2 wk |  | 1 wk | 4/6 wks | 1 day | 2/3 wks | 1/2 wks | 2 wks | 4 wks |  | 1/2 wks | 1/4 wks | 1/12 wks
Goods & Non Consulting Service
Head Office |  |  |  |  | 29: Plan vs. Actual
Production of TV Adverts | Corporate Affairs | 10 | CA 1 |  | LB |  |  | N/A | N/A | N/A | N/A | N/A | 15/01/2020 | 20/01/2020 | N/A | 24/01/2020 | 24/01/2020 | 27/01/2020 | 21/02/2020 | 28/02/2020 | 03/03/2020 | N/A | 17/03/2020 |  | 24/03/2020 | 27/03/2020 | 31/12/2020 | Plan
Actual
Production of TV Documentaries | Corporate Affairs | 12 | CA 2 |  | LB |  |  | N/A | N/A | N/A | N/A | N/A | 15/01/2020 | 20/01/2020 | N/A | 24/01/2020 | 24/01/2020 | 27/01/2020 | 21/02/2020 | 28/02/2020 | 03/03/2020 | N/A | 17/03/2020 |  | 24/03/2020 | 27/03/2020 | 31/12/2020 | Plan
Actual
Production of Radio Adverts | Corporate Affairs | 10 | CA 3 |  | LB |  |  | N/A | N/A | N/A | N/A | N/A | 15/01/2020 | 20/01/2020 | N/A | 24/01/2020 | 24/01/2020 | 27/01/2020 | 21/02/2020 | 28/02/2020 | 03/03/2020 | N/A | 17/03/2020 |  | 24/03/2020 | 27/03/2020 | 31/12/2020 | Plan
Actual
Production of print adverts | Corporate Affairs | 20 | CA 4 |  | LB |  |  | N/A | N/A | N/A | N/A | N/A | 15/01/2020 | 20/01/2020 | N/A | 24/01/2020 | 24/01/2020 | 27/01/2020 | 21/02/2020 | 28/02/2020 | 03/03/2020 | N/A | 17/03/2020 |  | 24/03/2020 | 27/03/2020 | 31/12/2020 | Plan
Actual
Translation of radio adverts | Corporate Affairs | 10 | CA 5 |  | LB | [7 empty] | 15/01/2020 | 20/01/2020 | N/A | 24/01/2020 | 24/01/2020 | 27/01/2020 | 21/02/2020 | 28/02/2020 | 03/03/2020 | N/A | 17/03/2020 |  | 24/03/2020 | 27/03/2020 | 31/12/2020 | Plan
Actual
Translation of flyers and brochures | Corporate Affairs/ ECIS |  | CA 6 |  | LB | [7 empty] | 15/01/2020 | 20/01/2020 | N/A | 24/01/2020 | 24/01/2020 | 27/01/2020 | 21/02/2020 | 28/02/2020 | 03/03/2020 | N/A | 17/03/2020 |  | 24/03/2020 | 27/03/2020 | 31/12/2020 | Plan
Actual
Airing of TV and radio programmes and adverts | Corporate Affairs |  |  |  | DB |  |  | N/A | N/A | N/A | N/A | N/A | 02/01/2020 | 09/01/2020 | N/A | 10/01/2020 | 15/01/2020 | 21/01/2020 | 04/02/2020 | 11/02/2020 | 18/02/2020 | N/A | N/A |  | 25/02/2020 | 11/03/2020 | Ongoing contract | Plan
Actual
Digital advertising | Corporate Affairs | 6 |  |  | SB | [7 empty] | 02/01/2020 | 09/01/2020 | N/A | N/A | 15/01/2020 | 21/01/2020 | 04/02/2020 | 11/02/2020 | 18/02/2020 | N/A | N/A |  | 25/02/2020 | 11/03/2020 | 31/12/2020 | Plan
Actual
Media Monitoring | Corporate Affairs |  |  |  | DB |  |  | N/A | N/A | N/A | N/A | N/A | 02/01/2020 | 09/01/2020 | N/A | 10/01/2020 | 15/01/2020 | 21/01/2020 | 04/02/2020 | 11/02/2020 | 18/02/2020 | N/A | N/A |  | 25/02/2020 | 11/03/2020 | 31/12/2020 | Plan
Actual
Brochures | Corporate Affairs | 18000 | CAP1 |  | SB |  |  | N/A | N/A | N/A | N/A | N/A | 08/01/2020 | 15/01/2020 | N/A | N/A | 17/01/2020 | 24/01/2020 | 07/02/2020 | 14/02/2020 | 21/02/2020 | N/A | N/A |  | 28/02/2020 | 28/02/2020 | 10/04/2020 | Plan
Actual
Brochures (Spireworks) | Corporate Affairs/ ECIS | 7,000 | CAP2 |  | SB | [7 empty] | 08/01/2020 | 15/01/2020 | N/A | N/A | 17/01/2020 | 24/01/2020 | 07/02/2020 | 14/02/2020 | 21/02/2020 | N/A | N/A |  | 28/02/2020 | 28/02/2020 | 10/04/2020 | Plan
Folders | Corporate Affairs | 5000 | CAP3 |  | SB |  |  | N/A | N/A | N/A | N/A | N/A | 08/01/2020 | 15/01/2020 | N/A | N/A | 17/01/2020 | 24/01/2020 | 07/02/2020 | 14/02/2020 | 21/02/2020 | N/A | N/A |  | 28/02/2020 | 28/02/2020 | 10/04/2020 | Plan
Actual
Flyers | Corporate Affairs | 3000 | CAP4 |  | SB |  |  | N/A | N/A | N/A | N/A | N/A | 08/01/2020 | 15/01/2020 | N/A | N/A | 17/01/2020 | 24/01/2020 | 07/02/2020 | 14/02/2020 | 21/02/2020 | N/A | N/A |  | 28/02/2020 | 28/02/2020 | 10/04/2020 | Plan
Actual
Flyers (Spireworks) | Corporate Affairs/ ECIS | 10,000 | CAP5 |  | SB | [7 empty] | 08/01/2020 | 15/01/2020 | N/A | N/A | 17/01/2020 | 24/01/2020 | 07/02/2020 | 14/02/2020 | 21/02/2020 | N/A | N/A |  | 28/02/2020 | 28/02/2020 | 10/04/2020 | Plan
Actual
License disc stickers | Corporate Affairs/ ECIS | 10,000 | CAP6 |  | SB | [7 empty] | 08/01/2020 | 15/01/2020 | N/A | N/A | 17/01/2020 | 24/01/2020 | 07/02/2020 | 14/02/2020 | 21/02/2020 | N/A | N/A |  | 28/02/2020 | 28/02/2020 | 10/04/2020 | Plan
Actual
NAPSA News | Corporate Affairs | 4 | CAP7 |  | SB |  |  | N/A | N/A | N/A | N/A | N/A | 08/01/2020 | 15/01/2020 | N/A | N/A | 17/01/2020 | 24/01/2020 | 07/02/2020 | 14/02/2020 | 21/02/2020 | N/A | N/A |  | 28/02/2020 | 28/02/2020 | ongoing | Plan
Actual
Business Cards | Corporate Affairs | 400 | CAP8 |  | SB |  |  | N/A | N/A | N/A | N/A | N/A | 08/01/2020 | 15/01/2020 | N/A | N/A | 17/01/2020 | 24/01/2020 | 07/02/2020 | 14/02/2020 | 21/02/2020 | N/A | N/A |  | 28/02/2020 | 28/02/2020 | 10/04/2020 | Plan
Actual
Maintenance of Billboards | Corporate Affairs | 10 |  |  | SB |  |  | N/A | N/A | N/A | N/A | N/A | 08/01/2020 | 15/01/2020 | N/A | N/A | 17/01/2020 | 24/01/2020 | 07/02/2020 | 14/02/2020 | 21/02/2020 | N/A | N/A |  | 28/02/2020 | 28/02/2020 | 10/04/2020 | Plan
Actual
Branded Umbrellas | Corporate Affairs | 100 |  |  | SB |  |  | N/A | N/A | N/A | N/A | N/A | 05/10/2020 | 12/10/2020 | N/A | N/A | N/A | 19/10/2020 | 30/10/2020 | 06/11/2020 | 13/11/2020 | N/A | N/A |  | 20/11/2020 | 20/11/2020 | 04/12/2020 | Plan
Actual
Pull-ups | Corporate Affairs | 30 | CAB 1 |  | ONB |  |  | N/A | N/A | N/A | N/A | N/A | 08/01/2020 | 15/01/2020 | N/A | N/A | 22/01/2020 | 03/02/2020 | 28/02/2020 | 06/03/2020 | 13/03/2020 | 18/03/2020 | 27/03/2020 |  | 30/03/2020 | 31/03/2020 | Ongoing | Plan
Actual
Tear Drops | Corporate Affairs | 30 | CAB 2 |  | ONB |  |  | N/A | N/A | N/A | N/A | N/A | 08/01/2020 | 15/01/2020 | N/A | N/A | 22/01/2020 | 03/02/2020 | 28/02/2020 | 06/03/2020 | 13/03/2020 | 18/03/2020 | 27/03/2020 |  | 30/03/2020 | 31/03/2020 | Ongoing | Plan
Actual
National Flags | Corporate Affairs | 65 | CAB3 |  | ONB |  |  | N/A | N/A | N/A | N/A | N/A | 08/01/2020 | 15/01/2020 | N/A | N/A | 22/01/2020 | 03/02/2020 | 28/02/2020 | 06/03/2020 | 13/03/2020 | 18/03/2020 | 27/03/2020 |  | 30/03/2020 | 31/03/2020 | Ongoing | Plan
Actual
Corporate Flags | Corporate Affairs | 65 | CAB4 |  | ONB |  |  | N/A | N/A | N/A | N/A | N/A | 08/01/2020 | 15/01/2020 | N/A | N/A | 22/01/2020 | 03/02/2020 | 28/02/2020 | 06/03/2020 | 13/03/2020 | 18/03/2020 | 27/03/2020 |  | 30/03/2020 | 31/03/2020 | Ongoing | Plan
Actual
Framing of Vision, Mission and Values | Corporate Affairs | 80 | CAB5 |  | ONB |  |  | N/A | N/A | N/A | N/A | N/A | 08/01/2020 | 15/01/2020 | N/A | N/A | 22/01/2020 | 03/02/2020 | 28/02/2020 | 06/03/2020 | 13/03/2020 | 18/03/2020 | 27/03/2020 |  | 30/03/2020 | 31/03/2020 | Ongoing | Plan
Actual
Gazebos | Corporate Affairs/ ECIS | 4 | CAB6 |  | ONB | [7 empty] | 08/01/2020 | 15/01/2020 | N/A | N/A | 22/01/2020 | 03/02/2020 | 28/02/2020 | 06/03/2020 | 13/03/2020 | 18/03/2020 | 27/03/2020 |  | 30/03/2020 | 31/03/2020 | Ongoing | Plan
Actual
Casual Shirts | Corporate Affairs | 700 | CAB7 |  | ONB |  |  | N/A | N/A | N/A | N/A | N/A | 08/01/2020 | 15/01/2020 | N/A | N/A | 22/01/2020 | 03/02/2020 | 28/02/2020 | 06/03/2020 | 13/03/2020 | 18/03/2020 | 27/03/2020 |  | 30/03/2020 | 31/03/2020 | Ongoing | Plan
Actual
Branded Chitenge (metres) | Corporate Affairs | 2000 | CAB8 |  | ONB | [7 empty] | 08/01/2020 | 15/01/2020 | N/A | N/A | 22/01/2020 | 03/02/2020 | 28/02/2020 | 06/03/2020 | 13/03/2020 | 18/03/2020 | 27/03/2020 |  | 30/03/2020 | 31/03/2020 | Ongoing | Plan
Actual
Round Neck T-shirts | Corporate Affairs/ ECIS | 800 | CAB9 |  | ONB |  |  | N/A | N/A | N/A | N/A | N/A | 08/01/2020 | 15/01/2020 | N/A | N/A | 22/01/2020 | 03/02/2020 | 28/02/2020 | 06/03/2020 | 13/03/2020 | 18/03/2020 | 27/03/2020 |  | 30/03/2020 | 31/03/2020 | Ongoing | Plan
Actual
Golf Shirts | Corporate Affairs/ECIS | 100 | CAB10 |  | ONB | [7 empty] | 08/01/2020 | 15/01/2020 | N/A | N/A | 22/01/2020 | 03/02/2020 | 28/02/2020 | 06/03/2020 | 13/03/2020 | 18/03/2020 | 27/03/2020 |  | 30/03/2020 | 31/03/2020 | Ongoing | Plan
Actual
Baseball caps | Corporate Affairs/ ECIS | 500 | CAB10 |  | ONB | [7 empty] | 08/01/2020 | 15/01/2020 | N/A | N/A | 22/01/2020 | 03/02/2020 | 28/02/2020 | 06/03/2020 | 13/03/2020 | 18/03/2020 | 27/03/2020 |  | 30/03/2020 | 31/03/2020 | Ongoing | Plan
Actual
Branded Pens | Corporate Affairs | 100 |  |  | SB |  |  | N/A | N/A | N/A | N/A | N/A | 08/01/2020 | 15/01/2020 | N/A | N/A | 17/01/2020 | 24/01/2020 | 07/02/2020 | 14/02/2020 | 21/02/2020 | N/A | N/A |  | 28/02/2020 | 28/02/2020 | 10/04/2020 | Plan
Actual
Executive Diaries | Corporate Affairs | 350 | CAG1 |  | ONB |  |  | N/A | N/A | N/A | N/A | N/A | 01/04/2020 | 08/04/2020 | N/A | N/A | 15/04/2020 | 22/04/2020 | 20/05/2020 | 03/06/2020 | 15/06/2020 | 29/06/2020 | 28/07/2019 |  | 10/08/2020 | 07/09/2020 | 09/11/2020 | Plan | 08/05/2019
Actual
Standard Diaries | Corporate Affairs | 500 | CAG2 |  | ONB |  |  | N/A | N/A | N/A | N/A | N/A | 01/04/2020 | 08/04/2020 | N/A | N/A | 15/04/2020 | 22/04/2020 | 20/05/2020 | 03/06/2020 | 15/06/2020 | 29/06/2020 | 28/07/2019 |  | 10/08/2020 | 07/09/2020 | 09/11/2020 | Plan | 08/05/2019
Actual
Note Books | Corporate Affairs | 7000 | CAG3 |  | ONB |  |  | N/A | N/A | N/A | N/A | N/A | 01/04/2020 | 08/04/2020 | N/A | N/A | 15/04/2020 | 22/04/2020 | 20/05/2020 | 03/06/2020 | 15/06/2020 | 29/06/2020 | 28/07/2019 |  | 10/08/2020 | 07/09/2020 | 09/11/2020 | Plan
Actual
Wall Calendars | Corporate Affairs | 800 | CAG4 |  | ONB |  |  | N/A | N/A | N/A | N/A | N/A | 01/04/2020 | 08/04/2020 | N/A | N/A | 15/04/2020 | 22/04/2020 | 20/05/2020 | 03/06/2020 | 15/06/2020 | 29/06/2020 | 28/07/2019 |  | 10/08/2020 | 07/09/2020 | 09/11/2020 | Plan
Actual
Desk Calendars | Corporate Affairs | 200 | CAG5 |  | ONB |  |  | N/A | N/A | N/A | N/A | N/A | 01/04/2020 | 08/04/2020 | N/A | N/A | 15/04/2020 | 22/04/2020 | 20/05/2020 | 03/06/2020 | 15/06/2020 | 29/06/2020 | 28/07/2019 |  | 10/08/2020 | 07/09/2020 | 09/11/2020 | Plan
Actual
Tent Calendars | Corporate Affairs | 800 | CAG6 |  | ONB |  |  | N/A | N/A | N/A | N/A | N/A | 01/04/2020 | 08/04/2020 | N/A | N/A | 15/04/2020 | 22/04/2020 | 20/05/2020 | 03/06/2020 | 15/06/2020 | 29/06/2020 | 28/07/2019 |  | 10/08/2020 | 07/09/2020 | 09/11/2020 | Plan
Actual
Christmas Cards | Corporate Affairs | 200 | CAG1A |  | SB |  |  | N/A | N/A | N/A | N/A | N/A | 05/10/2020 | 12/10/2020 | N/A | N/A | N/A | 19/10/2020 | 30/10/2020 | 06/11/2020 | 13/11/2020 | N/A | N/A |  | 20/11/2020 | 20/11/2020 | 04/12/2020 | Plan
Actual
Gift Bags | Corporate Affairs | 500 | CAG2A |  | SB |  |  | N/A | N/A | N/A | N/A | N/A | 05/10/2020 | 12/10/2020 | N/A | N/A | N/A | 19/10/2020 | 30/10/2020 | 06/11/2020 | 13/11/2020 | N/A | N/A |  | 20/11/2020 | 20/11/2020 | 04/12/2020 | Plan
Actual
Festive Gifts | Corporate Affairs | 300 | CAG3A |  | SB |  |  | N/A | N/A | N/A | N/A | N/A | 05/10/2020 | 12/10/2020 | N/A | N/A | N/A | 19/10/2020 | 30/10/2020 | 06/11/2020 | 13/11/2020 | N/A | N/A |  | 20/11/2020 | 20/11/2020 | 04/12/2020 | Plan
Actual
Shows and exhibitions | Corporate Affairs |  |  |  | LB |  |  | N/A | N/A | N/A | N/A | N/A | 15/01/2020 | 20/01/2020 | N/A | 24/01/2020 | 24/01/2020 | 27/01/2020 | 21/02/2020 | 28/02/2020 | 03/03/2020 | N/A | 17/03/2020 |  | 24/03/2020 | 27/03/2020 | 31/12/2020 | Plan
Actual
Motor Vehicle Branding | Corporate Affairs | 5 | CAB1A |  | ONB |  |  | N/A | N/A | N/A | N/A | N/A | 15/01/2020 | 20/01/2020 | N/A | 24/01/2020 | 24/01/2020 | 27/01/2020 | 21/02/2020 | 28/02/2020 | 03/03/2020 | N/A | 17/03/2020 |  | 24/03/2020 | 27/03/2020 | 31/12/2020 | Plan
Actual
Office Branding | Corporate Affairs | 8 | CAB2A |  | ONB | [7 empty] | 15/01/2020 | 20/01/2020 | N/A | 24/01/2020 | 24/01/2020 | 27/01/2020 | 21/02/2020 | 28/02/2020 | 03/03/2020 | N/A | 17/03/2020 |  | 24/03/2020 | 27/03/2020 | 31/12/2020 | Plan
Actual
Printing and Stationery | Finance |  |  |  | ONB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 02/01/2020 | 06/01/2020 | N/A | N/A | N/A | 13/01/2020 | 20/01/2020 | 22/01/2020 | 24/01/2020 | N/A | N/A |  | N/A | 24/01/2020 | 07/02/2020 | Plan | Procurement is as and when need arises
Actual
Staff Welfare | Finance |  |  |  | ONB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 02/01/2020 | 06/01/2020 | N/A | N/A | N/A | 13/01/2020 | 20/01/2020 | 22/01/2020 | 24/01/2020 | N/A | N/A |  | N/A | 24/01/2020 | 07/02/2020 | Plan | Procurement is as and when need arises
Actual
Cleaning materials | Finance |  |  |  | ONB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 02/01/2020 | 06/01/2020 | N/A | N/A | N/A | 13/01/2020 | 20/01/2020 | 22/01/2020 | 24/01/2020 | N/A | N/A |  | N/A | 24/01/2020 | 07/02/2020 | Plan | Procurement is as and when need arises
Actual
Computer Maintenance | IT |  |  |  | LB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 01/06/2020 | 12/06/2020 | N/A | 19/06/2020 | 26/06/2020 | 29/06/2020 | 24/07/2020 | 4/08/2020 | 14/08/2020 | N/A | 14/09/2020 |  | 2020-09-25 | 2020-10-09 |  | Plan
Actual
Computer and Sundries - Accessories | IT |  |  |  | SB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 02/01/2020 | 06/01/2020 | N/A | N/A | N/A | 08/01/2020 | 17/01/2020 | 20/01/2020 | 23/01/2020 | N/A | N/A |  | 2020-01-23 | 2020-01-23 |  | Plan | procured throught out the year as and when need arise
Actual
Hire Of Equipment | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-11-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | Plan | Contract Renewal
Actual
Performance Soft | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | 09/01/2020 | N/A | N/A | N/A | N/A | N/A | N/A | 16/01/2020 | N/A | N/A |  | N/A | N/A |  | Plan | License Renewal
Actual
S&P Capital IQ and Credit Risk | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | 09/01/2020 | N/A | N/A | N/A | N/A | N/A | N/A | 16/01/2020 | N/A | N/A |  | N/A | N/A |  | Plan | License Renewal
Actual
Budget Module | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-12-27 | 03/01/2020 | 17/01/2020 | 24/01/2020 | 31/01/2020 | 03/02/2020 | 14/02/2020 | 28/02/2020 | 6/03/2020 | N/A | 1/04/2020 |  | 10/04/2020 | 24/04/2020 |  | Plan
Actual
ERP Technology and Application Licenses (Inclusive of DB Security Licensing | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | 09/01/2020 | N/A | N/A | N/A | N/A | N/A | N/A | 16/01/2020 | N/A | N/A |  | N/A | N/A |  | Plan | License Renewal
Actual
ERP Support (Ad-hoc off-site Support) | IT |  |  |  | LB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 02/01/2020 | 06/01/2020 | N/A | 17/01/2020 | 24/01/2020 | 27/01/2020 | 28/02/2020 | 6/03/2020 | 13/03/2020 | N/A | 16/03/2020 |  | 20/04/2020 | 04/05/2020 |  | Plan
Actual
Oracle - TOD Enterprise | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | 09/01/2020 | N/A | N/A | N/A | N/A | N/A | N/A | 16/01/2020 | N/A | N/A |  | N/A | N/A |  | Plan
Actual
Microsoft - Volume License | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | 09/01/2020 | N/A | N/A | N/A | N/A | N/A | N/A | 16/01/2020 | N/A | N/A |  | N/A | N/A |  | Plan | Contract Renewal
Actual
Microsoft - Premier | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | 09/01/2020 | N/A | N/A | N/A | N/A | N/A | N/A | 16/01/2020 | N/A | N/A |  | N/A | N/A |  | Plan | Contract Renewal
Actual
End Point Anti Virus | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | 09/01/2020 | N/A | N/A | N/A | N/A | N/A | N/A | 16/01/2020 | N/A | N/A |  | N/A | N/A |  | Plan | Contract Renewal
Actual
ACL | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-07-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | Plan | Contract Renewal
Actual
ZICTA- SHORT CODE | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | Plan | Contract Renewal
Actual
ManageEngine-Log Event Viewer | IT |  |  |  | DB | [7 empty] | 2019-12-09 | 11/12/2019 | N/A | 13/12/2019 | 24/12/2019 | 27/12/2019 | 7/02/2020 | 14/02/2020 | 21/02/2020 | N/A | N/A |  | 28/02/2020 | 28/02/2020 |  | Plan | Additional module to existing modules
Actual
ManageEngine | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | 09/01/2020 | N/A | N/A | N/A | N/A | N/A | N/A | 16/01/2020 | N/A | N/A |  | N/A | N/A |  | Plan | Contract Renewal
Actual
Contact centre support | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | Plan | Contract Renewal
Actual
Firewall licenses | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | 09/01/2020 | N/A | N/A | N/A | N/A | N/A | N/A | 16/01/2020 | N/A | N/A |  | N/A | N/A |  | Plan | License renewal
Actual
Board Management Software | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | 09/01/2020 | N/A | N/A | N/A | N/A | N/A | N/A | 16/01/2020 | N/A | N/A |  | N/A | N/A |  | Plan | Contract Renewal
Actual
VICIDOCS | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | 09/01/2020 | N/A | N/A | N/A | N/A | N/A | N/A | 16/01/2020 | N/A | N/A |  | N/A | N/A |  | Plan | Contract Renewal
Actual
ERP Hardware Support (With Oracle Partner) and Training | IT |  |  |  | LB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-08 | 17/01/2020 | N/A | 24/01/2020 | 31/01/2020 | 03/02/2020 | 28/02/2020 | 09/03/2020 | 20/03/2020 | N/A | 27/03/2020 |  | 27/04/2020 | 08/05/2020 |  | Plan
Actual
MOBILE APP | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | Plan | Contract Renewal
Actual
eNAPSA | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 08/03/2019 | 18/03/2019 |  | Plan
Actual
SmartNet - MPLS | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-12-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | Plan | Contract Renewal
Actual
Hai - WAN | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-12-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | Plan | Contract Renewal
Actual
Zamnet Internet (8MB) | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | Plan | Contract Renewal
Actual
Zamtel Internet (16MB) | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | Plan | Contract Renewal
Actual
Zamtel MPLS | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-12-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | Plan | Contract Renewal
Actual
Telephone Service | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | Plan | Contract Renewal
Actual
Zamtel USSD | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | Plan | Contract Renewal
Actual
Airtel USSD | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | Plan | Contract Renewal
Actual
MTN USSD | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | Plan | Contract Renewal
Actual
4 Mbps Dedicated Internet for e-Channels | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | Plan | Contract Renewal
Actual
CheckPoint Maintenace & Support | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | 09/01/2020 | N/A | N/A | N/A | N/A | N/A | N/A | 16/01/2020 | N/A | N/A |  | 13/03/2020 | 27/03/2020 |  | Plan | Contract Renewal
Actual
Veeam Backup & Replication Support | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | 09/01/2020 | N/A | N/A | N/A | N/A | N/A | N/A | 16/01/2020 | N/A | N/A |  | N/A | N/A |  | Plan
Actual
Loan Management | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | 09/01/2020 | N/A | N/A | N/A | N/A | N/A | N/A | 16/01/2020 | N/A | N/A |  | N/A | N/A |  | Plan
Actual
NAPSA Mobile PlayStore/Apple Licensing | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | 09/01/2020 | N/A | N/A | N/A | N/A | N/A | N/A | 16/01/2020 | N/A | N/A |  | N/A | N/A |  | Plan
Actual
WinQS for Projects | IT (Projects) |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | 09/01/2020 | N/A | N/A | N/A | N/A | N/A | N/A | 16/01/2020 | N/A | N/A |  | N/A | N/A |  | Plan | License Renewal
Actual
Computer Software License (AutoCAD) | IT (Projects) | 1 |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | 09/01/2020 | N/A | N/A | N/A | N/A | N/A | N/A | 16/01/2020 | N/A | N/A |  | N/A | N/A |  | Plan | License Renewal
Actual
Computer Software License (eTABS) | IT (Projects) | 1 |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | 09/01/2020 | N/A | N/A | N/A | N/A | N/A | N/A | 16/01/2020 | N/A | N/A |  | N/A | N/A |  | Plan | License Renewal
Actual
Cloud Hosting Solution | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | Plan
Actual
Network Infrastructure Upgrade | IT |  |  |  | LB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | 13/01/2020 | N/A | 24/01/2020 | 31/01/2020 | 03/02/2020 | 14/02/2020 | 25/02/2020 | 06/03/2020 | N/A | N/A |  | 13/03/2020 | 27/03/2020 |  | Plan
Actual
Claim Payment System for mobile money | IT |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-02-04 | 18/02/2020 | N/A | 28/02/2020 | 6/03/2020 | 13/03/2020 | 27/03/2020 | 08/04/2020 | 17/04/2020 | N/A | 24/04/2020 |  | 25/05/2020 | 12/06/2020 |  | Plan
Actual
CaseWare for Financials | IT (Finance) |  |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  | Plan
Actual
Mobile Device | IT (C&B, Legal) | 89 | 1 |  | ONB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 14/1 /2020 | 24/01/2020 | N/A | N/A | 31/01/2020 | 03/02/2020 | 06/03/2020 | 18/03/2020 | 27/03/2020 | 06/04/2020 | N/A |  | 20/04/2020 | 27/04/2020 | 25/05/2020 | Plan
Actual
Phones for ECIS Agents | IT (C&B) | 60 | 2 |  | ONB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 14/1 /2020 | 24/01/2020 | N/A | N/A | 31/01/2020 | 03/02/2020 | 06/03/2020 | 18/03/2020 | 27/03/2020 | 06/04/2020 | N/A |  | 20/04/2020 | 27/04/2020 | 25/05/2020 | Plan
Actual
Printer Scanner | IT (C&B) | 16 | IT1 |  | ONB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-02-10 | 17/02/2020 | N/A | N/A | 28/02/2020 | 02/03/2020 | 03/04/2020 | 14/04/2020 | 24/04/2020 | N/A | N/A |  | 4/05/2020 | 15/05/2020 | 29/06/2020 | Plan
Actual
Receipt Printers | IT (C&B) | 9 | IT2 |  | ONB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-02-10 | 17/02/2020 | N/A | N/A | 28/02/2020 | 02/03/2020 | 03/04/2020 | 14/04/2020 | 24/04/2020 | N/A | N/A |  | 4/05/2020 | 15/05/2020 |  | Plan
Actual
A0 Plotter | IT (Projects) | 1 | IT3 |  | ONB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-02-10 | 17/02/2020 | N/A | N/A | 28/02/2020 | 02/03/2020 | 03/04/2020 | 14/04/2020 | 24/04/2020 | N/A | N/A |  | 4/05/2020 | 15/05/2020 | 29/06/2020 | Plan
Actual
Card printers | IT (C&b) | 12 | IT4 |  | ONB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-02-10 | 17/02/2020 | N/A | N/A | 28/02/2020 | 02/03/2020 | 03/04/2020 | 14/04/2020 | 24/04/2020 | N/A | N/A |  | 4/05/2020 | 15/05/2020 | 29/06/2020 | Plan
Actual
Scanners (DMS File Management) | IT (Head Office) | 10 | IT5 |  | ONB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-02-10 | 17/02/2020 | N/A | N/A | 28/02/2020 | 02/03/2020 | 03/04/2020 | 14/04/2020 | 24/04/2020 | N/A | N/A |  | 4/05/2020 | 15/05/2020 | 29/06/2020 | Plan
Actual
HP Laser Jet Colour M577 | IT (Investments) | 11 | IT6 |  | ONB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-02-10 | 17/02/2020 | N/A | N/A | 28/02/2020 | 02/03/2020 | 03/04/2020 | 14/04/2020 | 24/04/2020 | N/A | N/A |  | 4/05/2020 | 15/05/2020 | 29/06/2020 | Plan
Actual
Inverter Solution | IT (C&B) | 5 | 5 |  | SB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 02/01/2020 | 06/01/2020 | N/A | N/A | N/A | 08/01/2020 | 17/01/2020 | 20/01/2020 | 23/01/2020 | N/A | N/A |  | 2020-01-23 | 2020-01-23 | 03/03/2020 | Plan
Actual
Laptops | IT (All) | 80 | ITC 1 |  | ONB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-02-10 | 20/03/2020 | N/A | N/A | 28/02/2020 | 02/03/2020 | 03/04/2020 | 14/04/2020 | 24/04/2020 | N/A | N/A |  | 4/05/2020 | 15/05/2020 | 29/06/2020 | Plan
Actual
Computers | IT(C&B-NR) | 20 | ITC 2 |  | ONB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-02-10 | 20/03/2020 | N/A | N/A | 28/02/2020 | 02/03/2020 | 03/04/2020 | 14/04/2020 | 24/04/2020 | N/A | N/A |  | 4/05/2020 | 15/05/2020 | 29/06/2020 | Plan
Actual
IP Phones | IT (All) | 65 | DIT 1 |  | SB | [7 empty] | 2020-02-10 | 20/03/2020 | N/A | N/A | 25/03/2020 | 30/03/2020 | 17/04/2020 | 24/04/2020 | 04/05/2020 | N/A | N/A |  | 12/05/2020 | 12/05/2020 | 22/06/2020 | Plan
Actual
LCD Projector | IT (C&B) | 13 | DIT 2 |  | SB | [7 empty] | 2020-02-10 | 20/03/2020 | N/A | N/A | 25/03/2020 | 30/03/2020 | 17/04/2020 | 24/04/2020 | 04/05/2020 | N/A | N/A |  | 12/05/2020 | 12/05/2020 | 22/06/2020 | Plan
Actual
LCD Screen | IT (Projects) | 10 | DIT 3 |  | SB | [7 empty] | 2020-02-10 | 20/03/2020 | N/A | N/A | 25/03/2020 | 30/03/2020 | 17/04/2020 | 24/04/2020 | 04/05/2020 | N/A | N/A |  | 12/05/2020 | 12/05/2020 | 22/06/2020 | Plan
Actual
LED Projector | IT (Projects) | 3 | DIT 4 |  | SB | [7 empty] | 2020-02-10 | 20/03/2020 | N/A | N/A | 25/03/2020 | 30/03/2020 | 17/04/2020 | 24/04/2020 | 04/05/2020 | N/A | N/A |  | 12/05/2020 | 12/05/2020 | 22/06/2020 | Plan
Actual
Main UPS | IT | 1 |  |  | SB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-02-10 | 20/03/2020 | N/A | N/A | 25/03/2020 | 30/03/2020 | 17/04/2020 | 24/04/2020 | 04/05/2020 | N/A | N/A |  | 12/05/2020 | 12/05/2020 | 22/06/2020 | Plan
Actual
NAPSA Mobile VISA Payment Implementation | IT (C&B) | 1 |  |  | DB | [6 empty] | 01/06/2020 | 12/06/2020 | 2020-06-15 | 19/06/2020 | 26/06/2020 | 29/06/2020 | 24/07/2020 | 4/08/2020 | 14/08/2020 | N/A | 14/09/2020 | 2020-09-25 |  | 1900-01-13 |  | Plan
Enhancement of NAPSA Mobile solution for all modules | IT (C&B) | 1 |  |  | DB | [6 empty] | 01/06/2020 | 12/06/2020 | 2020-06-15 | 19/06/2020 | 26/06/2020 | 29/06/2020 | 24/07/2020 | 4/08/2020 | 14/08/2020 | N/A | 14/09/2020 | 500000 |  | 1900-01-13 |  | Plan
Enhancement of eNAPSA solution for all modules | IT (C&B) | 1 |  |  | DB | [6 empty] | 01/06/2020 | 12/06/2020 | 2020-06-15 | 19/06/2020 | 26/06/2020 | 29/06/2020 | 24/07/2020 | 4/08/2020 | 14/08/2020 | N/A | 14/09/2020 | 2020-09-25 |  | 1900-01-13 |  | Plan
ESB Solution Implementation | IT | 1 |  |  | LB | [6 empty] | 2020-02-04 | 18/02/2020 | 19/02/2020 | N/A | 6/03/2020 | 13/03/2020 | 27/03/2020 | 08/04/2020 | 17/04/2020 | N/A | 24/04/2020 | 25/05/2020 |  | 12/06/2020 |  | Plan
OSSIS Implementation and Operationalization | IT | 1 |  |  | DB | [6 empty] | 2020-02-04 | 18/02/2020 | 19/02/2020 | 28/02/2020 | 6/03/2020 | 13/03/2020 | 27/03/2020 | 08/04/2020 | 17/04/2020 | N/A | 24/04/2020 | 25/05/2020 |  | 12/06/2020 |  | Plan
Informal Sector Benefits Payments (Pension Admin) | IT (C&B-ECIS) | 1 |  |  | DB | [6 empty] | 01/06/2020 | 12/06/2020 | 2020-06-15 | 19/06/2020 | 26/06/2020 | 29/06/2020 | 24/07/2020 | 4/08/2020 | 14/08/2020 | N/A | 14/09/2020 | 2020-09-25 |  | 1900-01-13 |  | Plan
eBenefits Enhancement (eNAPSA Side) | IT (C&B-ECIS) | 1 |  |  | DB | [6 empty] | 2020-02-04 | 18/02/2020 | 19/02/2020 | 28/02/2020 | 6/03/2020 | 13/03/2020 | 27/03/2020 | 08/04/2020 | 17/04/2020 | N/A | 24/04/2020 | 25/05/2020 |  | 12/06/2020 |  | Plan
eRental Collections (portal and NAPSA Mobile) | IT (Investment) | 1 |  |  | LB | [6 empty] | 2020-02-04 | 18/02/2020 | 19/02/2020 | N/A | 6/03/2020 | 13/03/2020 | 27/03/2020 | 08/04/2020 | 17/04/2020 | N/A | 24/04/2020 | 25/05/2020 |  | 12/06/2020 |  | Plan
Litigation, Consultancy and Client Management | IT (Legal) | 1 |  |  | LB | [6 empty] | 2020-02-04 | 18/02/2020 | 19/02/2020 | N/A | 6/03/2020 | 13/03/2020 | 27/03/2020 | 08/04/2020 | 17/04/2020 | N/A | 24/04/2020 | 25/05/2020 |  | 12/06/2020 |  | Plan
Develop BI Dash Board for Pension Admin (Oracle BI) | IT (C&B) | 1 |  |  | LB | [6 empty] | 2020-02-04 | 18/02/2020 | 19/02/2020 | N/A | 6/03/2020 | 13/03/2020 | 27/03/2020 | 08/04/2020 | 17/04/2020 | N/A | 24/04/2020 | 25/05/2020 |  | 12/06/2020 |  | Plan
Internal Learning Portal 2020 | IT (HR) | 1 |  |  | LB | [6 empty] | 2020-02-04 | 18/02/2020 | 19/02/2020 | N/A | 6/03/2020 | 13/03/2020 | 27/03/2020 | 08/04/2020 | 17/04/2020 | N/A | 24/04/2020 | 25/05/2020 |  | 12/06/2020 |  | Plan
Complaint Management System Implementation | IT (Customer Services) | 1 |  |  | LB | [6 empty] | 2020-02-04 | 18/02/2020 | 19/02/2020 | N/A | 6/03/2020 | 13/03/2020 | 27/03/2020 | 08/04/2020 | 17/04/2020 | N/A | 24/04/2020 | 25/05/2020 |  | 12/06/2020 |  | Plan
Help Desk for the Call Centre Implementation | IT (Customer Services) | 1 |  |  | LB | [6 empty] | 2020-02-04 | 18/02/2020 | 19/02/2020 | N/A | 6/03/2020 | 13/03/2020 | 27/03/2020 | 08/04/2020 | 17/04/2020 | N/A | 24/04/2020 | 25/05/2020 |  | 12/06/2020 |  | Plan
IT Security Enhancements | IT | 1 |  |  | LB | [6 empty] | 2020-01-08 | 17/01/2020 | 19/01/2020 | N/A | 31/01/2020 | 03/02/2020 | 28/02/2020 | 09/03/2020 | 20/03/2020 | N/A | 27/03/2020 | 27/04/2020 |  | 08/05/2020 |  | Plan
Systems stabilization and enhancements | IT | 1 |  |  | LB | [6 empty] | 2020-01-08 | 17/01/2020 | 19/01/2020 | N/A | 31/01/2020 | 03/02/2020 | 28/02/2020 | 09/03/2020 | 20/03/2020 | N/A | 27/03/2020 | 27/04/2020 |  | 08/05/2020 |  | Plan
Secure signatures ( Procurement) | IT (Procurement) | 1 |  |  | DB | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-02 | 13/01/2020 | 19/01/2020 | 24/01/2020 | 31/01/2020 | 03/02/2020 | 14/02/2020 | 25/02/2020 | 06/03/2020 | N/A | N/A | 13/03/2020 |  | 27/03/2020 |  | Plan
Biometric on-boarding and Verification Kits | IT (C&B) | 1 |  |  | LB | [6 empty] | 2020-02-04 | 18/02/2020 | 19/02/2020 | N/A | 6/03/2020 | 13/03/2020 | 27/03/2020 | 08/04/2020 | 17/04/2020 | N/A | 24/04/2020 | 25/05/2020 |  | 12/06/2020 |  | Plan
Special Projects/ Research | Legal |  |  |  | DB | [7 empty] | 02/01/2020 | 06/01/2020 | N/A | 10/01/2020 | N/A | 13/01/2020 | 24/01/2020 | 27/01/2020 | 31/01/2020 | N/A | N/A |  | 31/01/2020 | 05/02/2020 | TBA | Plan
Actual
Board Training & Workshops | Legal |  |  |  | DB | [7 empty] | 02/01/2020 | 06/01/2020 | N/A | 10/01/2020 | N/A | 13/01/2020 | 24/01/2020 | 27/01/2020 | 31/01/2020 | N/A | N/A |  | 31/01/2020 | 05/02/2020 | TBA | Plan
Actual
Integrity Committee Expenses (Branded Items in form of Pens, Shirts and Pull-ups) | Legal/ Corporate Affairs |  |  |  | LB | [7 empty] | 2020-01-13 | 03/02/2020 | N/A | 14/02/2020 | 21/02/2020 | 28/02/2020 | 27/03/2020 | 03/04/2020 | 10/04/2020 | N/A | 17/04/2020 |  | 08/05/2020 | 15/05/2020 | 31/12/2020 | Plan
Actual
Levy Facilities Equipment Maintenance and Services - Fire, HVAC and Sliding Doors | Investment | 1 |  |  | DB | [7 empty] | 02/01/2020 | 06/01/2020 | N/A | 10/01/2020 | N/A | 13/01/2020 | 24/01/2020 | 27/01/2020 | 31/01/2020 | N/A | N/A |  | 31/01/2020 | 05/02/2020 | TBA | Plan
Actual
Operational Vehicles | Administration | 8 | MV1 |  | DB | 20/01/20 | [6 empty] | 2020-01-20 | 03/02/2020 | N/A | 12/02/2020 | 02/03/2020 | 10/03/2020 | 13/04/2020 | 22/04/2020 | 05/05/2020 | 14/05/2020 | N/A |  | 26/05/2020 | 26/05/2020 | 09/08/2020 | Plan
Actual
Duty Facilitating Vehicles | Administration | 17 | MV2 |  | DB | 20/01/20 | [6 empty] | 2020-01-20 | 03/02/2020 | N/A | 12/02/2020 | 02/03/2020 | 10/03/2020 | 13/04/2020 | 22/04/2020 | 05/05/2020 | 14/05/2020 | N/A |  | 26/05/2020 | 26/05/2020 | 09/08/2020 | Plan
Actual
Aircon | NR/SR/Admin | 73 |  |  | ONB | 3/02/2020 | 10/02/20 | N/A | 21/02/20 | 27/03/20 | 17/04/20 | 22/5/20 | 2020-02-03 | 10/02/2020 | N/A | 21/02/2020 | 27/03/20 | 17/04/20 | 22/05/2020 | 05/06/2020 | 19/06/2020 | 26/06/2020 | 10/07/2020 |  | 31/07/2020 | 14/08/2020 | 31/12/2020 | Plan
Actual
CCTV Monitors | Administration | 6 | AD1 |  | DB | 2020-03-02 | [6 empty] | 2020-03-02 | 9/03/2020 | N/A | 20/03/2020 | 27/03/2020 | 30/03/2020 | 17/04/2020 | 04/05/2020 | 15/05/2020 | N/A | 19/05/2020 |  | 22/06/2020 | 13/07/2020 | 31/12/2020 | Plan
Actual
CCTV Systems | Administration | 2 | AD2 |  | DB | 2020-03-02 | [6 empty] | 2020-03-02 | 9/03/2020 | N/A | 20/03/2020 | 27/03/2020 | 30/03/2020 | 17/04/2020 | 04/05/2020 | 15/05/2020 | N/A | 19/05/2020 |  | 22/06/2020 | 13/07/2020 | 31/12/2020 | Plan
Actual
Counters | NR/SR/Admin | 15 | FURN 1 |  | ONB | 20/01/20 | [6 empty] | 2020-01-20 | 03/02/2020 | N/A | N/A | 14/02/2020 | 1702/2020 | 20/03/2020 | 01/04/2020 | 10/04/2020 | 13/04/2020 | N/A |  | 27/04/2020 | 04/05/2020 | 07/07/2020 | Plan
Actual
Counter Chairs | NR & SR | 7 | FURN 2 |  | ONB | 20/01/20 | [6 empty] | 2020-01-20 | 03/02/2020 | N/A | N/A | 14/02/2020 | 1702/2020 | 20/03/2020 | 01/04/2020 | 10/04/2020 | 13/04/2020 | N/A |  | 27/04/2020 | 04/05/2020 | 07/07/2020 | Plan
Cosmos Couch | Administration | 1 | FURN 3 |  | ONB | [7 empty] | 2020-01-20 | 03/02/2020 | N/A | N/A | 14/02/2020 | 1702/2020 | 20/03/2020 | 01/04/2020 | 10/04/2020 | 13/04/2020 | N/A |  | 27/04/2020 | 04/05/2020 | 07/07/2020 | Plan
Actual
Airport Chairs | Administration | 10 | FURN 4 |  | ONB | [7 empty] | 2020-01-20 | 03/02/2020 | N/A | N/A | 14/02/2020 | 1702/2020 | 20/03/2020 | 01/04/2020 | 10/04/2020 | 13/04/2020 | N/A |  | 27/04/2020 | 04/05/2020 | 07/07/2020 | Plan
Actual
Arm Chairs | Administration | 18 | FURN 5 |  | ONB | 20/01/20 | [6 empty] | 2020-01-20 | 03/02/2020 | N/A | N/A | 14/02/2020 | 1702/2020 | 20/03/2020 | 01/04/2020 | 10/04/2020 | 13/04/2020 | N/A |  | 27/04/2020 | 04/05/2020 | 07/07/2020 | Plan
Actual
Astra Round Table (With 2 seats) | Administration | 3 | FURN 6 |  | ONB | 20/01/20 | [6 empty] | 2020-01-20 | 03/02/2020 | N/A | N/A | 14/02/2020 | 1702/2020 | 20/03/2020 | 01/04/2020 | 10/04/2020 | 13/04/2020 | N/A |  | 27/04/2020 | 04/05/2020 | 07/07/2020 | Plan
Actual
Boardroom Sets | Administration | 2 | FURN 7 |  | ONB | 20/01/20 | [6 empty] | 2020-01-20 | 03/02/2020 | N/A | N/A | 14/02/2020 | 1702/2020 | 20/03/2020 | 01/04/2020 | 10/04/2020 | 13/04/2020 | N/A |  | 27/04/2020 | 04/05/2020 | 07/07/2020 | Plan
Actual
Bench | NR/SR/Admin | 8 | FURN 8 |  | ONB | 20/01/20 | [6 empty] | 2020-01-20 | 03/02/2020 | N/A | N/A | 14/02/2020 | 1702/2020 | 20/03/2020 | 01/04/2020 | 10/04/2020 | 13/04/2020 | N/A |  | 27/04/2020 | 04/05/2020 | 07/07/2020 | Plan
Actual
Dictum Table Squares | Administration | 1 | FURN 9 |  | ONB | 20/01/20 | [6 empty] | 2020-01-20 | 03/02/2020 | N/A | N/A | 14/02/2020 | 1702/2020 | 20/03/2020 | 01/04/2020 | 10/04/2020 | 13/04/2020 | N/A |  | 27/04/2020 | 04/05/2020 | 07/07/2020 | Plan
Actual
Executive chairs | NR/SR/Admin | 3 | FURN 10 |  | ONB | 20/01/20 | [6 empty] | 2020-01-20 | 03/02/2020 | N/A | N/A | 14/02/2020 | 1702/2020 | 20/03/2020 | 01/04/2020 | 10/04/2020 | 13/04/2020 | N/A |  | 27/04/2020 | 04/05/2020 | 07/07/2020 | Plan
Actual
Executive Visitors Chairs | SR | 3 | FURN 11 |  | ONB | 20/01/20 | [6 empty] | 2020-01-20 | 03/02/2020 | N/A | N/A | 14/02/2020 | 1702/2020 | 20/03/2020 | 01/04/2020 | 10/04/2020 | 13/04/2020 | N/A |  | 27/04/2020 | 04/05/2020 | 07/07/2020 | Plan
Actual
Investments Boardroom Chairs | Administration | 12 | FURN 12 |  | ONB | 20/01/20 | [6 empty] | 2020-01-20 | 03/02/2020 | N/A | N/A | 14/02/2020 | 1702/2020 | 20/03/2020 | 01/04/2020 | 10/04/2020 | 13/04/2020 | N/A |  | 27/04/2020 | 04/05/2020 | 07/07/2020 | Plan
Actual
Front Office Counters | NR | 2 | FURN 13 |  | ONB | 20/01/20 | [6 empty] | 2020-01-20 | 03/02/2020 | N/A | N/A | 14/02/2020 | 1702/2020 | 20/03/2020 | 01/04/2020 | 10/04/2020 | 13/04/2020 | N/A |  | 27/04/2020 | 04/05/2020 | 07/07/2020 | Plan
Actual
Office Work station Solo | Administration | 16 | FURN 14 |  | ONB | 20/01/20 | [6 empty] | 2020-01-20 | 03/02/2020 | N/A | N/A | 14/02/2020 | 1702/2020 | 20/03/2020 | 01/04/2020 | 10/04/2020 | 13/04/2020 | N/A |  | 27/04/2020 | 04/05/2020 | 07/07/2020 | Plan
Actual
Sofa | SR/NR | 2 | FURN 15 |  | ONB | 20/01/20 | [6 empty] | 2020-01-20 | 03/02/2020 | N/A | N/A | 14/02/2020 | 1702/2020 | 20/03/2020 | 01/04/2020 | 10/04/2020 | 13/04/2020 | N/A |  | 27/04/2020 | 04/05/2020 | 07/07/2020 | Plan
Actual
Swivel Chairs | NR | 20 | FURN 16 |  | ONB | 20/01/20 | [6 empty] | 2020-01-20 | 03/02/2020 | N/A | N/A | 14/02/2020 | 1702/2020 | 20/03/2020 | 01/04/2020 | 10/04/2020 | 13/04/2020 | N/A |  | 27/04/2020 | 04/05/2020 | 07/07/2020 | Plan
Actual
Reception Tables | NR | 4 | FURN 17 |  | ONB | 20/01/20 | [6 empty] | 2020-01-20 | 03/02/2020 | N/A | N/A | 14/02/2020 | 1702/2020 | 20/03/2020 | 01/04/2020 | 10/04/2020 | 13/04/2020 | N/A |  | 27/04/2020 | 04/05/2020 | 07/07/2020 | Plan
Actual
Main Reception Chairs | Administration | 1 | FURN 18 |  | ONB | 20/01/20 | [6 empty] | 2020-01-20 | 03/02/2020 | N/A | N/A | 14/02/2020 | 1702/2020 | 20/03/2020 | 01/04/2020 | 10/04/2020 | 13/04/2020 | N/A |  | 27/04/2020 | 04/05/2020 | 07/07/2020 | Plan
Visitors' Chairs | NR | 18 | FURN 18 |  | ONB | 20/01/20 | [6 empty] | 2020-01-20 | 03/02/2020 | N/A | N/A | 14/02/2020 | 1702/2020 | 20/03/2020 | 01/04/2020 | 10/04/2020 | 13/04/2020 | N/A |  | 27/04/2020 | 04/05/2020 | 07/07/2020 | Plan
Visitors' Chairs - 3 way | NR/SR | 17 | FURN 19 |  | ONB | 20/01/20 | [6 empty] | 2020-01-20 | 03/02/2020 | N/A | N/A | 14/02/2020 | 1702/2020 | 20/03/2020 | 01/04/2020 | 10/04/2020 | 13/04/2020 | N/A |  | 27/04/2020 | 04/05/2020 | 07/07/2020
Factory Lockers | Administration | 30 | AD-A |  | SB | [7 empty] | 2020-05-04 | 18/05/2020 | N/A | N/A | 25/05/2020 | 01/06/2020 | 19/06/2020 | 06/07/2020 | 17/07/2020 | N/A | N/A |  | 24/07/2020 | 24/7/2020 | 07/09/2020 | Plan
Actual
Filing Cabinets | Administration | 18 | AD-B |  | SB | [7 empty] | 2020-05-04 | 18/05/2020 | N/A | N/A | 25/05/2020 | 01/06/2020 | 19/06/2020 | 06/07/2020 | 17/07/2020 | N/A | N/A |  | 24/07/2020 | 24/7/2020 | 07/09/2020 | Plan
Actual
Filing Cabinets (Single) | Administration | 16 | AD-C |  | SB | [7 empty] | 2020-05-04 | 18/05/2020 | N/A | N/A | 25/05/2020 | 01/06/2020 | 19/06/2020 | 06/07/2020 | 17/07/2020 | N/A | N/A |  | 24/07/2020 | 24/7/2020 | 07/09/2020 | Plan
Actual
Steel Shelves | NR/ SR/ Admin | 70 | AD-D |  | SB | [7 empty] | 2020-05-04 | 18/05/2020 | N/A | N/A | 25/05/2020 | 01/06/2020 | 19/06/2020 | 06/07/2020 | 17/07/2020 | N/A | N/A |  | 24/07/2020 | 24/7/2020 | 07/09/2020 | Plan
Actual
DSTv Kits | SR/NR | 13 |  |  | DB | [7 empty] | 2020-03-02 | 16/03/2020 | N/A | 27/06/2020 | 03/04/2020 | 06/04/2020 | 17/04/2020 | 30/04/2020 | 08/05/2020 | N/A | N/A |  | 08/05/2020 | 08/05/2020 | 30/06/2020 | Plan
Actual
Binding Machines Heavy Duty | Administration | 1 | OE 1 |  | SB | [7 empty] | 06/01/2020 | 09/01/2020 | N/A | N/A | N/A | 16/01/2020 | 23/01/2020 | 27/01/2020 | 30/01/2020 | N/A | N/A |  | N/A | 30/01/2020 | 13/02/2020 | Plan
Actual
Franking Machine | Finance | 1 | OE 2 |  | SB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 06/01/2020 | 09/01/2020 | N/A | N/A | N/A | 16/01/2020 | 23/01/2020 | 27/01/2020 | 30/01/2020 | N/A | N/A |  | N/A | 30/01/2020 | 13/02/2020 | Plan
Actual
Industrial Shredding Machine | Administration | 3 | OE 3 |  | SB | [7 empty] | 06/01/2020 | 09/01/2020 | N/A | N/A | N/A | 16/01/2020 | 23/01/2020 | 27/01/2020 | 30/01/2020 | N/A | N/A |  | N/A | 30/01/2020 | 13/02/2020 | Plan
Actual
Generator Sets | NR/SR | 5 |  |  | 6: ONB; 14: 2020-02-03; 15: 17/02/2020; 16: N/A; 17: N/A; 18: 02/03/2020; 19: 09/03/2020; 20: 10/04/2020; 21: 24/04/2020; 22: 08/05/2020; 23: 11/05/2020; 24: 26/05/2020; 26: 29/06/2020; 29: Plan
Actual
Industrial Trolleys | Administration | 6 |  |  | SB | [7 empty] | 2020-06-01 | 15/06/2020 | N/A | N/A | 26/06/2020 | 29/06/2020 | 17/07/2020 | 27/07/2020 | 07/08/2020 | N/A | N/A |  | 14/08/2020 | 14/08/2020 | 14/10/2020 | Plan
Actual
Refrigerators | NR/SR/Admin | 53 |  |  | SB | [7 empty] | 2020-03-02 | 16/03/2020 | N/A | N/A | 27/03/2020 | 30/03/2020 | 17/04/2020 | 04/05/2020 | 05/05/2020 | N/A | N/A |  | 15/05/2020 | 15/05/2020 | 22/06/2020 | Plan
Actual
Fan/ Cooler | Administration | 3 |  |  | SB | [7 empty] | 2020-07-13 | 20/07/2020 | N/A | N/A | 27/07/2020 | 24/08/20 | 24/08/2020 | 28/08/2020 | 04/09/2020 | N/A | N/A |  | 11/09/2020 | 11/09/2020 | 26/10/2020 | Plan
Actual
Hose Reels | NR/SR | 4 | CE 1 |  | SB | [7 empty] | 2020-03-02 | 16/03/2020 | N/A | N/A | 27/03/2020 | 30/03/2020 | 17/04/2020 | 04/05/2020 | 05/05/2020 | N/A | N/A |  | 15/05/2020 | 15/05/2020 | 22/06/2020 | Plan
Actual
Hoovers | SR | 7 | CE 2 |  | SB | [7 empty] | 2020-03-02 | 16/03/2020 | N/A | N/A | 27/03/2020 | 30/03/2020 | 17/04/2020 | 04/05/2020 | 05/05/2020 | N/A | N/A |  | 15/05/2020 | 15/05/2020 | 22/06/2020 | Plan
Actual
Lawn Mower | SR | 3 | CE 3 |  | SB | [7 empty] | 2020-03-02 | 16/03/2020 | N/A | N/A | 27/03/2020 | 30/03/2020 | 17/04/2020 | 04/05/2020 | 05/05/2020 | N/A | N/A |  | 15/05/2020 | 15/05/2020 | 22/06/2020 | Plan
Actual
Shining Machines | NR/SR | 9 | CE 4 |  | SB | 20/01/20 | [6 empty] | 2020-03-02 | 16/03/2020 | N/A | N/A | 27/03/2020 | 30/03/2020 | 17/04/2020 | 04/05/2020 | 05/05/2020 | N/A | N/A |  | 15/05/2020 | 15/05/2020 | 22/06/2020 | Plan
Actual
Polishing Machines | SR/ Administration | 8 | CE 5 |  | SB | [7 empty] | 2020-03-02 | 16/03/2020 | N/A | N/A | 27/03/2020 | 30/03/2020 | 17/04/2020 | 04/05/2020 | 05/05/2020 | N/A | N/A |  | 15/05/2020 | 15/05/2020 | 22/06/2020 | Plan
Actual
Vacuum Cleaner | SR | 6 | CE 5 |  | SB | [7 empty] | 2020-03-02 | 16/03/2020 | N/A | N/A | 27/03/2020 | 30/03/2020 | 17/04/2020 | 04/05/2020 | 05/05/2020 | N/A | N/A |  | 15/05/2020 | 15/05/2020 | 22/06/2020 | Plan
Actual
Safes | NR | 2 |  |  | SB | 2/03/20 | [6 empty] | 2020-03-02 | 16/03/2020 | N/A | N/A | 27/03/2020 | 30/03/2020 | 17/04/2020 | 04/05/2020 | 05/05/2020 | N/A | N/A |  | 15/05/2020 | 15/05/2020 | 22/06/2020 | Plan
Actual
Water Dispensers | NR | 3 |  |  | SB | [7 empty] | 01/04/2020 | 08/04/2020 | N/A | N/A | 15/04/2020 | 22/04/2020 | 20/05/2020 | 03/06/2020 | 15/06/2020 | 29/06/2020 | 28/07/2019 |  | 10/08/2020 | 07/09/2020 | 09/11/2020 | Plan
Actual
Staff Training | HR | 1 |  |  | ONB | 13/01/20 | [6 empty] | 2020-01-13 | 03/02/2020 | N/A | N/A | 14/02/2020 | 21/02/2020 | 20/03/2020 | 25/03/2020 | 27/03/2020 | 03/04/2020 | N/A |  | 10/04/2020 | 10/04/2020 | 30/07/2020 | Plan
Actual
Medical Scheme | HR | 1 |  |  | ONB | 1/01/20 | [6 empty] | 2020-01-14 | 31/01/2020 | N/A | N/A | 07/02/2020 | 14/02/2020 | 20/02/2020 | 27/02/2020 | 06/03/2020 | 13/03/2020 | 15/05/2020 |  | 22/05/2020 | 22/05/2020 | 30/05/2021 | Plan
Actual
Group Life Assurance | HR | 1 |  |  | ONB | 2020-01-01 | [6 empty] | 2020-01-14 | 31/01/2020 | N/A | N/A | 07/02/2020 | 14/02/2020 | 20/02/2020 | 27/02/2020 | 06/03/2020 | 13/03/2020 | 15/05/2020 |  | 22/05/2020 | 22/05/2020 | 30/05/2021 | Plan
Actual
Uniforms | HR | 1 |  |  | ONB | 2020-03-02 | [6 empty] | 2020-02-03 | 14/02/2020 | N/A | N/A | 21/02/2020 | 06/03/2020 | 03/04/2020 | 10/04/2020 | 17/04/2020 | 24/04/2020 | 26/06/2020 |  | 03/07/2020 | 03/07/2020 | 31/12/2020 | Plan
Actual
Group Personal Accident | HR | 1 | IN1 |  | ONB | 2020-01-01 | [6 empty] | 2020-01-14 | 31/01/2020 | N/A | N/A | 07/02/2020 | 14/02/2020 | 13/03/2020 | 27/03/2020 | 03/04/2020 | 10/04/2020 | 17/04/2020 |  | 15/05/2020 | 05/06/2020 | 31/12/2020 | Plan
Actual
Insurance (Motor Vehicles) | Admin | 1 | IN2 |  | ONB | 1/01/20 | [6 empty] | 2020-01-14 | 31/01/2020 | N/A | N/A | 07/02/2020 | 14/02/2020 | 13/03/2020 | 27/03/2020 | 03/04/2020 | 10/04/2020 | 17/04/2020 |  | 15/05/2020 | 05/06/2020 | 31/12/2020 | Plan
Actual
Office Insurance | Admin | 1 | IN3 |  | ONB | 1/01/20 | [6 empty] | 2020-01-14 | 31/01/2020 | N/A | N/A | 07/02/2020 | 14/02/2020 | 13/03/2020 | 27/03/2020 | 03/04/2020 | 10/04/2020 | 17/04/2020 |  | 15/05/2020 | 05/06/2020 | 31/12/2020 | Plan
Actual
Insurance Policy - Other | Admin | 1 | IN4 |  | ONB | 1/01/20 | [6 empty] | 2020-01-14 | 31/01/2020 | N/A | N/A | 07/02/2020 | 14/02/2020 | 13/03/2020 | 27/03/2020 | 03/04/2020 | 10/04/2020 | 17/04/2020 |  | 15/05/2020 | 05/06/2020 | 31/12/2020 | Plan
Actual
Security Charges | Admin | 1 |  |  | ONB | 1/01/20 | [6 empty] | 2020-01-13 | 03/02/2020 | N/A | N/A | 14/02/2020 | 21/02/2020 | 20/03/2020 | 25/03/2020 | 27/03/2020 | 03/04/2020 | N/A |  | 10/04/2020 | 10/04/2020 | 30/07/2020 | Plan
Actual
Staff Security Charges | Admin | 1 |  |  | SB | 1/01/20 | [6 empty] | 01/04/2020 | 08/04/2020 | N/A | N/A | 15/04/2020 | 22/04/2020 | 20/05/2020 | 03/06/2020 | 15/06/2020 | 29/06/2020 | 28/07/2019 |  | 10/08/2020 | 07/09/2020 | 09/11/2020 | Plan
Actual
Fleet Management Charge | Administration |  |  |  | LB | [7 empty] | 2020-01-13 | 03/02/2020 | N/A | 14/02/2020 | 21/02/2020 | 28/02/2020 | 27/03/2020 | 03/04/2020 | 10/04/2020 | N/A | 17/04/2020 |  | 08/05/2020 | 15/05/2020 | 31/12/2020 | Plan
Actual
Car Cleaning | Administration |  |  |  | SB | [7 empty] | 02/01/2020 | 06/01/2020 | N/A | N/A | 07/01/2020 | 08/01/2020 | 17/01/2020 | 20/01/2020 | 23/01/2020 | N/A | N/A |  | 2020-01-23 | 2020-01-23 | 31/12/2020 | Plan
Actual
Equipment Maintenance | Administration |  |  |  | LB | [7 empty] | 2020-01-13 | 03/02/2020 | N/A | 14/02/2020 | 21/02/2020 | 28/02/2020 | 27/03/2020 | 03/04/2020 | 10/04/2020 | N/A | 17/04/2020 |  | 08/05/2020 | 15/05/2020 | 31/12/2020 | Plan
Actual
Refuse Collection | Administration |  |  |  | SB | [7 empty] | 02/01/2020 | 06/01/2020 | N/A | N/A | 07/01/2020 | 08/01/2020 | 17/01/2020 | 20/01/2020 | 23/01/2020 | N/A | N/A |  | 2020-01-23 | 2020-01-23 | 31/12/2020 | Plan
Actual
Cleaning Services | Administration |  |  |  | ONB | [7 empty] | 2020-01-13 | 03/02/2020 | N/A | N/A | 14/02/2020 | 21/02/2020 | 20/03/2020 | 25/03/2020 | 27/03/2020 | 03/04/2020 | N/A |  | 10/04/2020 | 10/04/2020 | 30/07/2020 | Plan
Actual
Landscaping/ Plants | Administration |  | AD 1 |  | SB | [7 empty] | 2020-01-20 | 03/02/2020 | N/A | N/A | 14/02/2020 | 21/02/2020 | 13/03/2020 | 20/03/2020 | 27/03/2020 | N/A | N/A |  | 03/04/2020 | 03/04/2020 | 31/12/2020 | Plan
Actual
Fumigation | Administration |  | AD 2 |  | SB | [7 empty] | 2020-01-20 | 03/02/2020 | N/A | N/A | 14/02/2020 | 21/02/2020 | 13/03/2020 | 20/03/2020 | 27/03/2020 | N/A | N/A |  | 03/04/2020 | 03/04/2020 | 31/12/2020 | Plan
Actual
Office Relocation | Administration |  |  |  | SB | [7 empty] | 02/01/2020 | 06/01/2020 | N/A | N/A | 07/01/2020 | 08/01/2020 | 17/01/2020 | 20/01/2020 | 23/01/2020 | N/A | N/A |  | 2020-01-23 | 2020-01-23 | 31/12/2020 | Plan
Actual
Actuarial Fees | C & B |  |  |  | DB | [7 empty] | 2020-03-02 | 16/03/2020 | N/A | 27/03/2020 | 03/04/2020 | 06/04/2020 | 24/04/2020 | 08/05/2020 | 15/05/2020 | N/A | 22/05/2020 |  | 19/06/2020 | 26/06/2020 | 31/12/2020 | Plan
Actual
Employer/Employee Seminars | C & B |  |  |  | LB | [7 empty] | 2020-01-13 | 03/02/2020 | N/A | 14/02/2020 | 21/02/2020 | 28/02/2020 | 27/03/2020 | 03/04/2020 | 10/04/2020 | N/A | 17/04/2020 |  | 08/05/2020 | 15/05/2020 | 31/12/2020 | Plan
Actual
Pension Reform Support | C & B |  |  |  | LB | [7 empty] | 2020-01-13 | 03/02/2020 | N/A | 14/02/2020 | 21/02/2020 | 28/02/2020 | 27/03/2020 | 03/04/2020 | 10/04/2020 | N/A | 17/04/2020 |  | 08/05/2020 | 15/05/2020 | 31/12/2020 | Plan
Actual
Social Security Cards | C & B |  |  |  | SB | [7 empty] | 2020-01-20 | 03/02/2020 | N/A | N/A | 14/02/2020 | 21/02/2020 | 13/03/2020 | 20/03/2020 | 27/03/2020 | N/A | N/A |  | 03/04/2020 | 03/04/2020 | 31/12/2020 | Plan
Actual
HIV/AIDS (Wellness) Policy | Human Resource |  |  |  | SB | [7 empty] | 2020-01-20 | 03/02/2020 | N/A | N/A | 14/02/2020 | 21/02/2020 | 13/03/2020 | 20/03/2020 | 27/03/2020 | N/A | N/A |  | 03/04/2020 | 03/04/2020 | 31/12/2020 | Plan
Actual
Works
Property Description- Property Development/ Refurbishment works
Refurbishment of Provident House - Solwezi | Investments | 1 |  |  | NCB | [7 empty] | 03/03/2020 | 05/03/2020 | N/A | N/A | 06/03/2020 | 16/03/2020 | 17/04/2020 | 24/04/2020 | 24/04/2020 | 28/04/2020 | 14/05/2020 |  | 22/05/2020 | 29/05/2020 | TBA | Plan
Actual
Refurbishment of Provident House - Mongu | Investments | 1 |  |  | NCB | [7 empty] | 03/03/2020 | 05/03/2020 | N/A | N/A | 06/03/2020 | 16/03/2020 | 17/04/2020 | 24/04/2020 | 24/04/2020 | 28/04/2020 | 14/05/2020 |  | 22/05/2020 | 29/05/2020 | TBA | Plan
Actual
ZNPF Properties Refurbishment & Modernisation of Shoprite – Ndola | Investments | 1 |  |  | NCB | [7 empty] | 04/08/2020 | 06/08/2020 | N/A | N/A | 07/08/2020 | 11/08/2020 | 11/09/2020 | 18/09/2020 | 18/09/2020 | 22/09/2020 | 6/10/2020 |  | 09/10/2020 | 16/10/2020 | TBA | Plan
Actual
ZNPF Properties Refurbishment & Modernisation of Clems House - Chingola | Investments | 1 |  |  | SB | [7 empty] | 04/08/2020 | 06/08/2020 | N/A | N/A | 07/08/2020 | 11/08/2020 | 11/09/2020 | 18/09/2020 | 18/09/2020 | N/A | N/A |  | 25/09/2020 | 25/09/2020 | TBA | Plan
Actual
Redevelopment of Chipata Provident House - Chipata | Investments | 1 |  |  | NCB | [7 empty] | 03/08/2020 | 05/08/2020 | N/A | N/A | 07/08/2020 | 11/8/2020 | 11/9/2020 | 18/09/2020 | 18/09/2020 | 22/9/2020 | 07/10/2020 |  | 14/10/2020 | 16/10/2020 | TBA | Plan
Actual
Mufurila Mixed use development - Construction Works | Investments | 1 |  |  | LB | [7 empty] | 2019-09-26 | 2019-10-02 | N/A | 2019-10-04 | 2019-10-16 | 2019-10-21 | 2019-11-29 | 2019-12-20 | 2019-12-20 | N/A | 2020-01-06 |  | 2020-01-13 | 2020-01-17 | 31/07/2021 | Plan | Awarded
Actual
Mbala Construction of New Office Block | Investments | 1 |  |  | NCB | [7 empty] | 03/03/2020 | 05/03/2020 | N/A | N/A | 06/03/2020 | 16/03/2020 | 17/04/2020 | 24/04/2020 | 24/04/2020 | 28/04/2020 | 14/05/2020 |  | 22/05/2020 | 29/05/2020 | TBA | Plan
Actual
Water reservoir, tank and stand and booster pump - Senanga | Investments | 1 |  |  | SB | [7 empty] | 06/01/2020 | 08/01/2020 | N/A | N/A | 10/01/2020 | 14/01/2020 | 14/02/2020 | 21/02/2020 | 21/02/2020 | N/A | 10/03/2020 |  | 19/03/2020 | 25/03/2020 | TBA | Plan
Actual
Works & Fencing of Baobab Land | Investments | 1 |  |  | NCB | [7 empty] | 29/06/2020 | 01/07/2020 | N/A | N/A | 03/07/2020 | 09/07/2020 | 07/08/2020 | 14/08/2020 | 14/08/2020 | 18/08/2020 | 03/09/2020 |  | 10/09/2020 | 15/09/2020 | TBA | Plan
Actual
Countrywide barelands construction of visible pillars | Investments | 1 |  |  | 6: LB; 14: 21/06/2019; 15: 13/09/2019; 16: N/A; 17: 27/09/2019; 18: 27/09/2019; 19: 03/10/2019; 20: 22/11/2019; 21: 24/12/2019; 22: 27/12/2019; 29: Plan
Actual
Chitanda House - Kabwe (Roof repair) | Investments | 1 |  |  | LB | [7 empty] | 11/10/2019 | 15/10/2019 | N/A | 15/11/2019 | 15/11/2019 | 18/11/2019 | 13/12/2019 | 26/12/2019 | 03/01/2020 | 07/01/2020 | 21/1/2020 |  | 28/01/2020 | 31/01/2020 | TBA | Plan
Actual
ZNPF Properties Refurbishment & Modernisation of Electra House - Lusaka - Works | Investments | 1 |  |  | NCB | [7 empty] | 04/08/2020 | 06/08/2020 | N/A | N/A | 07/08/2020 | 11/08/2020 | 11/09/2020 | 18/09/2020 | 18/09/2020 | 22/09/2020 | 6/10/2020 |  | 09/10/2020 | 16/10/2020 | TBA | Plan
Actual
Riverpark Infrastructure Construction Works | Investments | 1 |  |  | DB | [7 empty] | 25/11/2019 | 27/11/2019 | 9/12/2019 | 29/11/2019 | 06/12/2019 | 18/12/2019 | 24/01/2020 | 31/01/2020 | 31/01/2020 | N/A | 05/02/2020 |  | 12/02/2020 | 14/02/2020 | TBA | Plan
Actual
Refurbishment works - Mkushi Phase II | Investments | 1 |  |  | LB | [7 empty] | 03/02/2020 | 05/02/2020 | N/A | 07/02/2020 | 07/02/2020 | 11/02/2020 | 11/03/2020 | 20/03/2020 | 20/03/2020 | N/A | 25/03/2020 |  | 01/04/2020 | 03/04/2020 | TBA | Plan
Actual
ZNPF Properties Refurbishment & Modernisation of Provident Arcade - Kitwe - Works | Investments | 1 |  |  | NCB | [7 empty] | 29/06/2020 | 01/07/2020 | N/A | N/A | 03/07/2020 | 09/07/2020 | 07/08/2020 | 14/08/2020 | 14/08/2020 | 18/08/2020 | 03/09/2020 |  | 10/09/2020 | 15/09/2020 | TBA | Plan
Actual
ZNPF Properties Redevelopment of Office and Record of Kingstone House – Ndola | Investments | 1 |  |  | NCB | [7 empty] | 29/06/2020 | 01/07/2020 | N/A | N/A | 03/07/2020 | 09/07/2020 | 07/08/2020 | 14/08/2020 | 14/08/2020 | 18/08/2020 | 03/09/2020 |  | 10/09/2020 | 15/09/2020 | TBA | Plan
Actual
Area Office - Kafue - Works | Investments | 1 |  |  | NCB | [7 empty] | 03/08/2020 | 05/08/2020 | N/A | N/A | 07/08/2020 | 11/8/2020 | 11/9/2020 | 18/09/2020 | 18/09/2020 | 22/9/2020 | 07/10/2020 |  | 14/10/2020 | 16/10/2020 | TBA | Plan
Actual
Area Office - Kasama - Works | Investments | 1 |  |  | NCB | [7 empty] | 03/08/2020 | 05/08/2020 | N/A | N/A | 07/08/2020 | 11/8/2020 | 11/9/2020 | 18/09/2020 | 18/09/2020 | 22/9/2020 | 07/10/2020 |  | 14/10/2020 | 16/10/2020 | TBA | Plan
Actual
ECL Office Block Conversion (Change of use) - Works | Investments | 1 |  |  | LB | [7 empty] | 04/05/2020 | 06/05/2020 | N/A | 08/05/2020 | 08/05/2020 | 12/05/2020 | 13/06/2020 | 20/06/2020 | 20/06/2020 | N/A | 01/07/2020 |  | 03/07/2020 | 09/07/2020 | TBA | Plan
Actual
Southgate Makeni 1500 units - Site Plan, Infrastructure designs and housing units BOQs | Investments | 1 |  |  | NCB | [7 empty] | 02/06/2020 | 04/06/2020 | 05/06/2020 | N/A | 06/06/2020 | 09/06/2020 | 10/07/2020 | 17/07/2020 | 17/07/2020 | 21/07/2020 | 06/08/2020 |  | 14/08/2020 | 18/08/2020 | TBA | Plan
Actual
Solwezi Kazhiba 100 units - Infrastructure and houisng construction work | Investments | 1 |  |  | LB | [7 empty] | 18/09/2019 | 25/09/2019 | N/A | 04/10/2019 | 16/10/2019 | 17/10/2020 | 29/11/2019 | 09/12/2019 | 20/12/2019 | N/A | 2020-01-06 |  | 2020-01-13 | 2020-01-17 |  | Plan | Procurement process done
Actual
Chinsali 50 units - Intrastructure and Housing Construction Works | Investments | 1 |  |  | LB | [7 empty] | 18/09/2019 | 25/09/2019 | N/A | 04/10/2019 | 16/10/2019 | 17/10/2020 | 29/11/2019 | 09/12/2019 | 20/12/2019 | N/A | 2020-01-06 |  | 2020-01-13 | 2020-01-17 |  | Plan | Procurement process done
Actual
Chitambo 50 units -Intrastructure and housing construction works | Investments | 1 |  |  | LB | [7 empty] | 18/09/2019 | 25/09/2019 | N/A | 04/10/2019 | 16/10/2019 | 17/10/2020 | 29/11/2019 | 09/12/2019 | 20/12/2019 | N/A | 2020-01-06 |  | 2020-01-13 | 2020-01-17 |  | Plan | Procurement process done
Actual
Surveying, Demarcation and Beaconing Services on the Remaining bare Lands Kalulushi Housing Complex and Northgate | Investments | 1 |  |  | SB | [7 empty] | 06/01/2020 | 08/01/2020 | N/A | N/A | 10/01/2020 | 14/01/2020 | 14/02/2020 | 21/02/2020 | 21/02/2020 | N/A | 10/03/2020 |  | 19/03/2020 | 25/03/2020 | TBA | Plan | Procurement process done
Actual
KEY
PPP | Public Private Partnership
NCB | National Competitive Bidding
ONB | Open National Bidding (National Competitive Bidding)
SB | Simplified Bidding
LB | Limited Bidding
LS | Limited Selection
DB | Direct Bidding
DS | Direct Selection
EMC | Executive Management Committee
BOQ | Bill of Quantities
TORs | Terms of Reference
PSU | Procurement & Stores Unit
ICB | International Competitive Bidding
C&B | Contribution and Benefits
IT | Information Technology
HR & ADMIN | Human Resources and Administration
CA | Corporate Affairs
S & BP | Strategy and Business Performance
ECIS | Extension of Coverage to the Informal Sector (Project under Contributions and Benefits)
Shaded Areas in Column 3 & 4 | Consolidated as one tender at tender Execution Stage

## APP-CONS - NAPSA 2020
PROCUREMENT PLAN FOR CONSULTANCY SERVICES - INTERNAL USE
Name of the Procuring Entity: | [5 empty] | NAPSA
Financial Year: | [5 empty] | 2020
Description* | User | Basic Data | [5 empty] | Notice/ Advert Issued By Procurement | Request for Expression of Interest |  |  |  |  | Preparation of RFP Documents |  |  |  | Invitation of proposals and approval for award | [8 empty] | Contract Finalization |  |  | Plan vs. Actual
|  | Tender No. | Lot Number |  | Procurement Method | Contract Type | USER |  | Invitation |  | Evaluation |  | USER |  |  |  |  | Consultant Proposals |  | Proposal Evaluation Technical (T) & Financial (F)
|  |  |  | Estimated amount I ZMW .000 |  |  | Submission of TORs by User to Procurement |  | Invitation Date | Closing-Opening | Submission Eval. Rpt | Approval of Shortlist by MPC | Submission of TORs/ functional specs by User | Prep & Submission by PSU | Approval by PCRC/ EMC /USER | Approval of Direct/Limited Selection by MPC | Clearance by ZPPA for direct selection | Invitation Date | Submission/ Closing Opening Date | Submission Evaluation Report (T) | Approval of Evaluation Report (T) by MPC | Opening Financial Proposals | Submission Eval. Report (T) (F) | Approval Eval Report (T) (F) by MPC | Notice of intention to award Date | Vetting/ Ratification of contracts By AG | Contract Amount in K '000 | Contract award | Contract Signature |  | Comment
1 |  | 2 | 3 |  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Normal Duration of Proc. Steps | [7 empty] | 3-6 wks | 1-1.5 wks | 2 - 3 wks | 1- 3 wks | 1 wk |  | 1-2 wks |  |  | 1 wk | 2 wk | 12 wks | 1-3 wks | 1 wk | 1-2 wks | 1-3 wks | 1 wk | 2 wks | 4 wks |  |  |  | Plan
Actual
ZNPF Properties Refurbishment & Modernisation of Electra House - Lusaka - Consultancy | Investments |  | 1 |  | OS | [7 empty] | 28/01/2019 | 30/01/2019 | N/A | 01/02/2019 | N/A | 20/02/2019 | 29/03/2019 | 17/05/2019 | 17/05/2019 | 24/05/2019 | 07/06/2019 | 07/06/2019 | 28/10/2019 | TBA |  | TBA | TBA | Plan | procured in 2019, implementation in 2020
Actual
ZNPF Properties Refurbishment & Modernisation of Provident Arcade - Kitwe - Consultancy | Investments |  | 1 |  | OS | [7 empty] | 13/01/2020 | 16/01/2020 | NA | NA | 17/01/2020 | 21/01/2020 | 21/02/2020 | 28/02/2020 | 28/02/2020 | 3/03/2020 | 06/03/2020 | 06/03/2020 | 24/03/2020 | 31/03/2020 |  | 03/04/2020 | 09/04/2020 | Plan
Actual
ZNPF Properties Redevelopment of Office and Record of Kingstone House – Consultancy - Ndola | Investments |  | 1 |  | OS | [7 empty] | 13/01/2020 | 16/01/2020 | NA | NA | 17/01/2020 | 21/01/2020 | 21/02/2020 | 28/02/2020 | 28/02/2020 | 3/03/2020 | 06/03/2020 | 06/03/2020 | 24/03/2020 | 31/03/2020 |  | 03/04/2020 | 09/04/2020 | Plan
Actual
Levy Bus Station Conceptualisation | Investments |  | 1 |  | OS | [7 empty] | 03/02/2020 | 05/02/2020 | NA | NA | 07/02/2020 | 11/02/2020 | 06/03/2020 | 13/03/2020 | 13/03/2020 | 17/03/2020 | 20/03/2020 | 20/03/2020 | 24/03/2020 | 03/04/2020 |  | 10/04/2020 | 16/04/2020 | Plan
Actual
Area Office - Kafue - Consultancy | Investments |  | 1 |  | OS | [7 empty] | 01/06/2020 | 03/06/2020 | NA | NA | 05/06/2020 | 09/06/2020 | 10/07/2020 | 17/07/2020 | 17/07/2020 | 21/07/2020 | 24/07/2020 | 24/07/2020 | 28/07/2020 | 11/08/2020 |  | 21/08/2020 | 26/08/2020 | Plan
Actual
Area Office - Kasama - Consultancy - Consultancy | Investments |  | 1 |  | OS | [7 empty] | 03/02/2020 | 05/02/2020 | NA | NA | 07/02/2020 | 11/02/2020 | 06/03/2020 | 13/03/2020 | 13/03/2020 | 17/03/2020 | 20/03/2020 | 20/03/2020 | 24/03/2020 | 03/04/2020 |  | 10/04/2020 | 16/04/2020 | Plan
Actual
ECL Office Block Conversion (Change of use) - Consultancy | Investments |  | 1 |  | LS | [7 empty] | 13/01/2020 | 16/01/2020 | NA | 17/1/2020 | 17/01/2020 | 21/01/2020 | 21/02/2020 | 28/02/2020 | 28/02/2020 | 3/03/2020 | 06/03/2020 | 06/03/2020 | N/A | 13/03/2020 |  | 20/03/2020 | 26/03/2020 | Plan
Actual
Consultancy Services for the development of Baobab Land | Investments |  | 1 |  | LS | [7 empty] | 13/01/2020 | 16/01/2020 | NA | 17/01/2020 | 17/01/2020 | 21/01/2020 | 21/02/2020 | 28/02/2020 | 28/02/2020 | 3/03/2020 | 06/03/2020 | 06/03/2020 | N/A | 13/03/2020 |  | 20/03/2020 | 26/03/2020 | Plan
Actual
Southgate Makeni 1500 units - Site Plan, Infrastructure designs and housing units BOQs | Investments |  | 1 |  | DS | [7 empty] | 26/11/2019 | 12/12/2019 | NA | 16/10/2019 | 06/12/2019 | 11/12/2019 | 17/01/2020 | 24/01/2020 | 24/01/2020 | 28/01/2020 | 31/01/2020 | 31/01/2020 | N/A | 7/02/2020 |  | 11/02/2020 | 14/02/2020 | Plan
Actual
Area Office - Kafue Land Acquisition | Investments |  | 1 |  | OS | [7 empty] | 06/01/2020 | 08/01/2020 | NA | NA | 10/01/2020 | 14/01/2020 | 14/02/2020 | 21/02/2020 | 21/02/2020 | 25/02/2020 | 28/02/2020 | 28/02/2020 | 03/03/2020 | 27/03/2020 |  | 03/04/2020 | 09/04/2020 | Plan
Actual
Southgate Makeni 1500 units - Engineering design services | Investments |  | 1 |  | DS | [7 empty] | 03/03/2020 | 05/03/2020 | N/A | 06/0/2020 | 06/2020 | 10/03/2020 | 09/04/2020 | 17/04/2020 | 17/04/2020 | 21/04/2020 | 24/04/2020 | 24/04/2020 | N/A | 30/04/2020 |  | 07/05/2020 | 14/05/2020 | Plan | Procured in 2019, implementation is in 2020
Actual
ZNPF Selected properties supplimentary market study | Investments |  | 1 |  | LS | [7 empty] | 13/01/2020 | 16/01/2020 | NA | 17/01/2020 | 17/01/2020 | 21/01/2020 | 21/02/2020 | 28/02/2020 | 28/02/2020 | 3/03/2020 | 06/03/2020 | 06/03/2020 | 24/03/2020 | 31/03/2020 |  | 03/04/2020 | 09/04/2020 | Plan
Actual
Redevelopment of Chipata Provident House - Chipata | Investments |  | 1 |  | LS | [7 empty] | 01/06/2020 | 03/06/2020 | 05/06/2020 | 05/06/2020 | 05/06/2020 | 09/06/2020 | 10/07/2020 | 17/07/2020 | 17/07/2020 | 21/07/2020 | 24/07/2020 | 24/07/2020 | N/A | 11/08/2020 |  | 21/08/2020 | 26/08/2020 | Plan
Actual
Call Centre Enhancements | IT |  |  |  | LS | [7 empty] | 24/02/2020 | 03/03/2020 | 13/03/2020 | 20/03/2020 | N/A | 23/03/2020 | 24/04/2020 | 07/05/2020 | 15/05/2020 | 22/05/2020 | 29/05/2020 | 05/06/2020 | N/A | 06/07/2020 |  | 13/07/2020 | 31/07/2020 | Plan
Actual
Private Cloud Enhancements | IT |  |  |  | LS | [7 empty] | 24/02/2020 | 03/03/2020 | 13/03/2020 | 20/03/2020 | N/A | 23/03/2020 | 24/04/2020 | 07/05/2020 | 15/05/2020 | 22/05/2020 | 29/05/2020 | 05/06/2020 | N/A | 06/07/2020 |  | 13/07/2020 | 31/07/2020 | Plan
Actual
Claim Payment System (using mobile money solution) | IT |  |  |  | DS | [7 empty] | 3/02/2020 | 14/02/2020 | 21/02/2020 | 28/02/2020 | 02/03/2020 | 16/03/2020 | 27/03/2020 | 06/04/2020 | 17/04/2020 | 22/04/2020 | 27/04/2020 | 08/05/2020 | N/A | 08/06/2020 |  | 15/06/2020 | 06/07/2020 | Plan
Actual
Record Digitization Software | IT |  |  |  | LS | [7 empty] | 24/02/2020 | 03/03/2020 | 13/03/2020 | 20/03/2020 | N/A | 23/03/2020 | 24/04/2020 | 07/05/2020 | 15/05/2020 | 22/05/2020 | 29/05/2020 | 05/06/2020 | N/A | 06/07/2020 |  | 13/07/2020 | 31/07/2020 | Plan
Actual
HR |  | Human Resources
PR |  | Public Relations
OIS |  | Open International Selection
SB |  | Simplified Bidding
LS |  | Limited Selection
DS |  | Direct Selection
EMC |  | Executive Management Committee
TORs |  | Terms of Reference
PSU |  | Procurement & Stores Unit
C&B |  | Contribution and Benefits
IT |  | Information Technology
HR |  | Human Resources
PR |  | Public Relations
OIS |  | Open International Selection